## Work List
Exported on: 2026-10-01 14:50:06
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: CHHULHA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ANUPPUR / ANUPPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repr MainT of Cmpnd wall for govt schools / Repair and Maintenance of Compound wall for government run schools for Community | Repair & Maint of Community infrastructure | 1746002012/AV/22012034516556 — बौन्द्री वाल निर्माणं माध्यमिकशाला छुल्हा मीटर 428 | Ongoing | 1497747.73 | 0 | 2021-10-06
ANUPPUR / ANUPPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1746002012/AV/22012034549316 — गोसला निर्माण पकारिहा ग्राम पंचायत छुलहा | Ongoing | 3804449.17 | 0 | 2021-03-02
ANUPPUR / ANUPPUR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1746002012/DP/22012034424414 — वृक्षारोपण सामुदायिक कार्य दानूबाबा एरिया (भाग-1) खसरा नं. 3 ग्राम पकरिहा | Ongoing | 544000 | 156640 | 2018-08-09
ANUPPUR / ANUPPUR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1746002012/DP/22012034432630 — वृक्षारोपण कार्य दानूबाबा एरिया (भाग 2) | Ongoing | 544000 | 52270 | 2018-09-19
ANUPPUR / ANUPPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1746002012/DP/22012034603774 — Vasudha Vandan Antargat Plantation Kary..P/S. Chapraatola chhulha | Ongoing | 55847.4 | 0 | 2023-10-08
ANUPPUR / ANUPPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1746002012/IF/22012034607172 — कटेल सेट निर्माण कान्हेया प्रजापति | Ongoing | 101273.16 | 0 | 2021-09-02
ANUPPUR / ANUPPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1746002012/IF/22012034612671 — कैटल सेट निर्माण कार्य चरकी बाई गोंड बीझा टोला | Ongoing | 101273.16 | 0 | 2020-11-10
ANUPPUR / ANUPPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1746002012/IF/22012034612672 — कैटल सेट कार्य निर्माण जगदीश यदव बीझा टोला | Ongoing | 101273.16 | 0 | 2020-11-10
ANUPPUR / ANUPPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1746002012/IF/22012034612679 — कैटेल सेट निर्माण कार्य रामगोपाल | Ongoing | 101273.16 | 0 | 2020-11-10
ANUPPUR / ANUPPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1746002012/IF/22012034612683 — कैटेल सेट निर्माण कार्य बोद्दा सिंह बिझातोला | Ongoing | 101273.16 | 0 | 2020-11-10
ANUPPUR / ANUPPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1746002012/IF/22012034632432 — cattel set nirman dinesh singh/tilakraj | Ongoing | 101804.91 | 0 | 2021-11-03
ANUPPUR / ANUPPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1746002012/IF/22012034632433 — cattel set nirman bhaiyalal gupta/jamuna prashad | Ongoing | 101804.91 | 0 | 2021-01-19
ANUPPUR / ANUPPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/110994 — Construction of IAY House -IAY REG. NO. MP-46-002-012-002/095 | Approved | 28500 | 0 | 2015-11-05
ANUPPUR / ANUPPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/110995 — Construction of IAY House -IAY REG. NO. MP-46-002-012-003/0084 | Approved | 28500 | 0 | 2015-11-05
ANUPPUR / ANUPPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/110996 — Construction of IAY House -IAY REG. NO. MP-46-002-012-003/088 | Approved | 28500 | 0 | 2015-11-05
ANUPPUR / ANUPPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/110997 — Construction of IAY House -IAY REG. NO. MP-46-002-012-003/16 | Approved | 28500 | 0 | 2015-11-05
ANUPPUR / ANUPPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/110998 — Construction of IAY House -IAY REG. NO. MP-46-002-012-003/35 | Approved | 28500 | 0 | 2015-11-05
ANUPPUR / ANUPPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/110999 — Construction of IAY House -IAY REG. NO. MP-46-002-012-003/36 | Approved | 28500 | 0 | 2015-11-05
ANUPPUR / ANUPPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/111000 — Construction of IAY House -IAY REG. NO. MP-46-002-012-003/79 | Approved | 28500 | 0 | 2015-11-05
ANUPPUR / ANUPPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/1606763 — Construction of IAY House -IAY REG. NO. MP1603467 | Approved | 28500 | 0 | 2018-04-03
ANUPPUR / ANUPPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/1609942 — Construction of IAY House -IAY REG. NO. MP2688995 | Approved | 28500 | 0 | 2018-04-03
ANUPPUR / ANUPPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/1609943 — Construction of IAY House -IAY REG. NO. MP2689141 | Approved | 28500 | 0 | 2018-04-03
ANUPPUR / ANUPPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/1610129 — Construction of IAY House -IAY REG. NO. MP2743623 | Approved | 28500 | 0 | 2018-04-03
ANUPPUR / ANUPPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/1610353 — Construction of IAY House -IAY REG. NO. MP2801584 | Approved | 28500 | 0 | 2018-04-03
ANUPPUR / ANUPPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/1610897 — Construction of IAY House -IAY REG. NO. MP2878556 | Approved | 28500 | 0 | 2018-04-03
ANUPPUR / ANUPPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/1839025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2610616 | Approved | 28500 | 0 | 2018-06-05
ANUPPUR / ANUPPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/1839336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2875553 | Approved | 28500 | 0 | 2018-06-05
ANUPPUR / ANUPPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/1847421 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2645627 | Approved | 28500 | 0 | 2018-06-13
ANUPPUR / ANUPPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/1847427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2667883 | Approved | 28500 | 0 | 2018-06-13
ANUPPUR / ANUPPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/1882058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5335193 | Ongoing | 28500 | 0 | 2020-07-12
ANUPPUR / ANUPPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/2199719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5468189 | Ongoing | 28500 | 0 | 2019-11-21
ANUPPUR / ANUPPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/2438195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5556515 | Approved | 28500 | 0 | 2020-04-30
ANUPPUR / ANUPPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/2438379 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5565248 | Approved | 28500 | 0 | 2020-04-30
ANUPPUR / ANUPPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/3042719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4068466 | Approved | 28500 | 0 | 2021-01-06
ANUPPUR / ANUPPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/404388 — Construction of IAY House -IAY REG. NO. MP1227515 | Approved | 28500 | 0 | 2017-01-23
ANUPPUR / ANUPPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/5532275 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151778173 | Ongoing | 28500 | 0 | 2025-11-10
ANUPPUR / ANUPPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/606785 — Construction of IAY House -IAY REG. NO. MP1083519 | Approved | 28500 | 0 | 2017-02-05
ANUPPUR / ANUPPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1746002012/IF/IAY/979403 — Construction of IAY House -IAY REG. NO. MP3858517 | Approved | 28500 | 0 | 2017-04-19
ANUPPUR / ANUPPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1746002012/IF/YD/22012035627474 — EK BAGIYA MAA KE NAAM HITGRAHI SAKUNTALA/ RAMESH YADAV | Ongoing | 193537.88 | 2000 | 2025-12-04
ANUPPUR / ANUPPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1746002012/IF/YD/22012035655097 — Khettalab Nirman Dinesh Singh Bijhatola | New | 0 | 0 | 2026-01-03
ANUPPUR / ANUPPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1746002012/IF/YD/22012035655105 — Khettalab Nirman Dwarika Singh Vijhatola | New | 0 | 0 | 2026-01-03
ANUPPUR / ANUPPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1746002012/IF/YD/22012035661304 — Khettalab Nirman Kalyan Singh Chhulha | New | 0 | 0 | 2026-01-26
ANUPPUR / ANUPPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1746002012/RS/22012034654728 — कचरा घरनिर्माण वार्ड नं.12 भाग 2 | Physically Completed | 14133.23 | 0 | 2022-05-25 | 2026-09-26
ANUPPUR / ANUPPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1746002012/RS/22012034654729 — कचरा घरनिर्माण वार्ड नं.13 भाग 2 | Physically Completed | 14133.23 | 0 | 2022-05-25 | 2026-09-26
ANUPPUR / ANUPPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1746002012/RS/22012034654736 — कचरा घरनिर्माण वार्ड नं.17 | Physically Completed | 14133.23 | 0 | 2022-05-25 | 2026-09-26
ANUPPUR / ANUPPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1746002012/WC/VB/22012035330339 — M/S SCHOOL PAKARIHA ROOP TOP WATER HARVESTING | Approved | 0 | 0 | 2026-04-14
ANUPPUR / ANUPPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1746002012/WC/VB/22012035330343 — PANCHAYAT BHAVAN ROOP TOP WATER HARVESTING | Approved | 0 | 0 | 2026-04-14
ANUPPUR / ANUPPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1746002012/WC/VB/YD/22012035336055 — Roof top rain wat. har. str. in gov/panchayat bldg | Approved | 0 | 0 | 2026-08-17