## Work List
Exported on: 2026-10-02 08:58:16
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SALARGONDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ANUPPUR / PUSHPRAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1746004104/IC/22012034889978 — Nirmalneer nirman karya sundar lal baiga ke ghar ke pass salargondi | Ongoing | 605674.76 | 64118.85 | 2025-04-19
ANUPPUR / PUSHPRAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1746004104/IC/22012034889979 — Nirmalneer nirman karya Rammilan singh ke ghar ke pass salargondi | Ongoing | 605674.76 | 0 | 2026-05-12
ANUPPUR / PUSHPRAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1746004104/IC/22012034889980 — Nirmalneer nirman karya Godu vishwakarma ke ghar ke pass harradadar | Approved | 605674.76 | 0 | 2025-04-01
ANUPPUR / PUSHPRAJGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1746004104/IF/22012035263278 — khet talab nirman kary baisakhu singh/ baniya singh | Approved | 0 | 0 | 2024-10-02
ANUPPUR / PUSHPRAJGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1746004104/IF/22012035263282 — khet talab nirman kary Sajan singh/Dhan singh | New | 0 | 0 | 2024-10-02
ANUPPUR / PUSHPRAJGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1746004104/IF/22012035263283 — khet talab nirman kary Sarita bai / shivcharan singh | New | 0 | 0 | 2024-10-02
ANUPPUR / PUSHPRAJGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746004104/IF/22012035300071 — Khettalab Nirman Karya Ramji/Dhanna | New | 0 | 0 | 2025-01-28
ANUPPUR / PUSHPRAJGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746004104/IF/22012035310467 — Khettalab Nirman Karya Sanjay Yadav/Devlal Yadav | New | 0 | 0 | 2025-01-27
ANUPPUR / PUSHPRAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746004104/IF/22012035319912 — CTR Khettalab Nirman Karya Prem Singh/Moti Singh | New | 0 | 0 | 2025-04-01
ANUPPUR / PUSHPRAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746004104/IF/22012035319933 — CTR Khettalab Nirman Karya Budhva/Baniya | New | 0 | 0 | 2025-04-01
ANUPPUR / PUSHPRAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746004104/IF/22012035320143 — CTR Khettalab Nirman Karya Ajay Yadav/ Devlal | New | 0 | 0 | 2025-04-01
ANUPPUR / PUSHPRAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746004104/IF/22012035320165 — CTR Khettalab Nirman Karya Tilakram/ Dashrath | New | 0 | 0 | 2025-04-01
ANUPPUR / PUSHPRAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1746004104/IF/22012035320179 — CTR Khettalab Nirman Karya Bhesam Lal/ Komal | New | 0 | 0 | 2025-04-01
ANUPPUR / PUSHPRAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746004104/IF/22012035327989 — CATTEL SHED NIRMAN KARYA RADHA BAI/GANESH PRASAD | Approved | 0 | 0 | 2025-04-01
ANUPPUR / PUSHPRAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746004104/IF/22012035329284 — CATTEL SHED NIRMAN KARYA SHYAMWATI BAI/KOMAL | Approved | 0 | 0 | 2025-04-01
ANUPPUR / PUSHPRAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746004104/IF/22012035329286 — CATTEL SHED NIRMAN KARYA SEETA BAI/RAMLU BAIGA | Approved | 0 | 0 | 2025-04-01
ANUPPUR / PUSHPRAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1746004104/IF/22012035329289 — CATTEL SHED NIRMAN KARYA DURGA NAYAK/BHAMA NAYAK | Approved | 0 | 0 | 2025-04-01
ANUPPUR / PUSHPRAJGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1746004104/IF/IAY/2995290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5619972 | Approved | 28500 | 0 | 2021-01-13
ANUPPUR / PUSHPRAJGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1746004104/IF/IAY/4416675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151874773 | Ongoing | 28500 | 0 | 2024-03-04
ANUPPUR / PUSHPRAJGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1746004104/IF/IAY/4418024 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151875667 | Ongoing | 28500 | 0 | 2024-03-04
ANUPPUR / PUSHPRAJGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1746004104/IF/IAY/4436950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151780782 | Ongoing | 28500 | 0 | 2024-04-12
ANUPPUR / PUSHPRAJGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1746004104/IF/IAY/4454465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151766809 | Ongoing | 28500 | 0 | 2024-02-22
ANUPPUR / PUSHPRAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1746004104/IF/IAY/5651189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151767878 | Physically Completed | 24795 | 0 | 2025-10-10 | 2026-07-14
ANUPPUR / PUSHPRAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1746004104/IF/IAY/5651191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151767710 | Physically Completed | 24795 | 0 | 2025-10-10 | 2026-07-14
ANUPPUR / PUSHPRAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1746004104/IF/IAY/5687054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151772458 | Physically Completed | 24795 | 0 | 2025-11-20 | 2026-07-14
ANUPPUR / PUSHPRAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1746004104/IF/IAY/5687067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151767713 | Physically Completed | 24795 | 0 | 2025-10-10 | 2026-07-14
ANUPPUR / PUSHPRAJGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1746004104/WC/22012034820035 — CTR Check dam nirman karya padramada nala harradadar me | Ongoing | 1497084.65 | 0 | 2021-10-07
ANUPPUR / PUSHPRAJGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1746004104/WC/22012034981397 — ctr gebiyan strakchar nirnadh kary haradadar nala kramak 3 me 2 nag | Ongoing | 442653.57 | 0 | 2022-09-07
ANUPPUR / PUSHPRAJGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1746004104/WC/22012034981434 — ctr gebiyan strakchar nirnadh kary haradadar nala kramank 5me 2 nag | Ongoing | 395719.27 | 0 | 2022-09-14
ANUPPUR / PUSHPRAJGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1746004104/WC/22012035035744 — nirmal neer koop nirman kary bidhayak tirah pas | Ongoing | 295607.37 | 0 | 2023-04-28
ANUPPUR / PUSHPRAJGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1746004104/WC/VB/YD/22012035336076 — Roof top rain wat. har. str. in gov/panchayat bldg | Approved | 0 | 0 | 2026-07-14