## Work List
Exported on: 2026-09-14 21:28:41
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: RAMAKHEDA KHURD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BURHANPUR / KHAKNAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1747008065/AV/22012034663988 — ग्रामीण खेल मैदानग्राम पंचायत रामाखेड़ा खुर्द | New | 0 | 0 | 2025-01-14
BURHANPUR / KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1747008065/FR/22012034324018 — निस्तार तालाब निर्माण कार्य ग्राम पंचायत रामाखेड़ा खुर्द परसराम लालू खेत के पास | New | 0 | 0 | 2025-01-14
BURHANPUR / KHAKNAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1747008065/IF/22012034406457 — HITESHI KAPIL DHARA KUP MAY KHET TALAB NIRMAN KARY(GAJARASINGH SUKHRAM)G.P.RAMAKHEDA KHURD | Ongoing | 230000 | 0 | 2018-05-22
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1747008065/IF/22012035349864 — FARM FOUND NIRMAN KARY RAMDAS DAYLU KE KHT ME GRAM PANCHYAT RAMAKHEDA KHURD | Ongoing | 227717.32 | 0 | 2025-04-29
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1747008065/IF/22012035350158 — FARM FOUND NIRMAN KARY BHIYALAL CUNIYA KE KHET ME GRAM PANCHYAT RAMAKHEDA KHURD | New | 0 | 0 | 2025-04-14
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035439675 — JGSA 2025 RECHARGE STRUCTURE KAPIL DHARA KUP UMESH DARIYASINGH KE KHET MEIN | New | 0 | 0 | 2025-04-29
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035439808 — JGSA 2025 RECHARGE STRUCTURE KAPIL DHARA KUP KE KHET MEIN | New | 0 | 0 | 2025-04-29
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035564113 — JGS RECHARGE PIT DUGWELL SURESH BABULAL GP RAMAKHEDAKHURD | Approved | 0 | 0 | 2025-04-14
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035564120 — JGS RECHARGE PIT DUGWELL MOJILAL SUKHRAM GP RAMAKHEDAKHURD | Approved | 0 | 0 | 2025-04-14
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035564128 — JGS RECHARGE PIT DUGWELL JAWAHARLAL SANU GP RAMAKHEDAKHURD | Approved | 0 | 0 | 2025-06-05
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035564133 — JGS RECHARGE PIT DUGWELL SHOBHARAM MANANG GP RAMAKHEDAKHURD | Approved | 0 | 0 | 2025-06-05
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035564138 — JGS RECHARGE PIT DUGWELL GULABSING SHOBHASING GP RAMAKHEDAKHURD | Approved | 0 | 0 | 2025-06-05
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035564145 — JGS RECHARGE PIT DUGWELL PARASRAM RINGA GP RAMAKHEDAKHURD | Approved | 0 | 0 | 2025-06-05
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035564151 — JGS RECHARGE PIT DUGWELL DHARAMLAL AASHARAM GP RAMAKHEDAKHURD | Approved | 0 | 0 | 2025-06-05
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035564157 — JGS RECHARGE PIT DUGWELL KARAN LALU GP RAMAKHEDAKHURD | Approved | 0 | 0 | 2025-06-05
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035564162 — JGS RECHARGE PIT DUGWELL SHANTILAL MUNSHI GP RAMAKHEDAKHURD | Approved | 0 | 0 | 2025-06-05
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035564168 — JGS RECHARGE PIT DUGWELL SABULAL SANU GP RAMAKHEDAKHURD | Approved | 0 | 0 | 2025-06-05
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035564171 — JGS RECHARGE PIT DUGWELL SHOBHASING BATU GP RAMAKHEDAKHURD | Approved | 0 | 0 | 2025-06-05
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035564172 — JGS RECHARGE PIT DUGWELL MANSING ONKAR GP RAMAKHEDAKHURD | Approved | 0 | 0 | 2025-06-05
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035564174 — JGS RECHARGE PIT DUGWELL SUKAIBAI GP RAMAKHEDAKHURD | Approved | 0 | 0 | 2025-06-05
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035564179 — JGS RECHARGE PIT DUGWELL RAMESHWAR ANOKHILAL GP RAMAKHEDAKHURD | Approved | 0 | 0 | 2025-06-05
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035564183 — JGS RECHARGE PIT DUGWELL BABULAL SHIKARI GP RAMAKHEDAKHURD | Approved | 0 | 0 | 2025-06-05
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035564189 — JGS RECHARGE PIT DUGWELL KALIRAM GHISIYA GP RAMAKHEDAKHURD | Approved | 0 | 0 | 2025-06-05
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035564191 — JGS RECHARGE PIT DUGWELL KISAN BHAULAL GP RAMAKHEDAKHURD | Approved | 0 | 0 | 2025-06-05
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035564197 — JGS RECHARGE PIT DUGWELL REEMU RAMBHAU GP RAMAKHEDAKHURD | Approved | 0 | 0 | 2025-06-05
BURHANPUR / KHAKNAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1747008065/IF/22012035567056 — JGSA 2025 DUGWELL RECHARGE STRUCTURE KAPIL DHARA KUP SUNDERLAL MUNSHI KE KHET MEIN | Approved | 0 | 0 | 2025-06-08
BURHANPUR / KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/4534762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102270327 | Physically Completed | 23490 | 0 | 2024-12-12 | 2026-08-23
BURHANPUR / KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/4817436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100634054 | Ongoing | 27000 | 3600 | 2024-12-26
BURHANPUR / KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/4906824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100928892 | Ongoing | 27000 | 3600 | 2025-03-15
BURHANPUR / KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/4906988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102463186 | Ongoing | 27000 | 3600 | 2025-03-08
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/4935168 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100778647 | Ongoing | 27000 | 3600 | 2025-06-04
BURHANPUR / KHAKNAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/4939663 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105998855 | Ongoing | 27000 | 0 | 2026-04-26
BURHANPUR / KHAKNAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/4943290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115209372 | Ongoing | 27000 | 0 | 2026-04-02
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/4987205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100999960 | Ongoing | 27000 | 0 | 2025-07-25
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/4987543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102462272 | Ongoing | 27000 | 0 | 2025-11-18
BURHANPUR / KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/4987544 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102462334 | Ongoing | 27000 | 7200 | 2025-03-22
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/4987877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100928778 | Ongoing | 27000 | 0 | 2025-10-11
BURHANPUR / KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/4987878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100929232 | Completed | 23490 | 0 | 2025-03-22 | 2026-08-06
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/4989156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105423337 | Ongoing | 27000 | 0 | 2025-07-18
BURHANPUR / KHAKNAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/4994949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115207303 | Ongoing | 27000 | 0 | 2025-03-22
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5423592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115205687 | Ongoing | 27000 | 3600 | 2025-06-02
BURHANPUR / KHAKNAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5426533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105970334 | Physically Completed | 23490 | 0 | 2026-04-02 | 2026-08-09
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5428109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102271406 | Completed | 23490 | 0 | 2025-11-11 | 2026-08-06
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5429339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115209096 | Physically Completed | 23490 | 0 | 2025-07-25 | 2026-08-09
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5429651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102462221 | Ongoing | 27000 | 1800 | 2025-06-04
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5430808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100929341 | Physically Completed | 23490 | 0 | 2025-05-21 | 2026-08-16
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5517741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100778473 | Completed | 23490 | 0 | 2025-06-02 | 2026-08-06
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5523379 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102270923 | Ongoing | 27000 | 0 | 2025-11-18
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5583666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100778193 | Ongoing | 27000 | 3600 | 2025-05-27
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5599709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100848874 | Physically Completed | 23490 | 0 | 2025-06-02 | 2026-08-09
BURHANPUR / KHAKNAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5599994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102169179 | Ongoing | 27000 | 0 | 2026-07-21
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5624417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100633435 | Ongoing | 27000 | 0 | 2025-06-02
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5656443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105550479 | Ongoing | 27000 | 0 | 2025-09-20
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5656634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102194310 | Ongoing | 27000 | 0 | 2025-08-07
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5657092 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100778137 | Ongoing | 27000 | 0 | 2025-08-08
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5657267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102270137 | Ongoing | 27000 | 0 | 2025-11-11
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5670891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102270846 | Ongoing | 27000 | 0 | 2025-08-08
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5682346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102270728 | Completed | 23490 | 0 | 2025-12-09 | 2026-08-06
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5688518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100847223 | Physically Completed | 23490 | 0 | 2025-11-25 | 2026-08-23
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5753156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102270264 | Physically Completed | 23490 | 0 | 2025-11-11 | 2026-08-09
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5814498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102169252 | Physically Completed | 23490 | 0 | 2025-12-02 | 2026-08-09
BURHANPUR / KHAKNAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5874635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115209234 | Ongoing | 27000 | 0 | 2026-04-09
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5874697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100778165 | Ongoing | 27000 | 0 | 2026-01-23
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5874998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102270529 | Physically Completed | 23490 | 0 | 2026-02-13 | 2026-08-09
BURHANPUR / KHAKNAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1747008065/IF/IAY/5875062 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105970285 | Ongoing | 27000 | 0 | 2026-01-30
BURHANPUR / KHAKNAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1747008065/LD/22012034942576 — podharopan panchayat bhavan se mahupal tak gp ramakhedakhurd | Ongoing | 337706.47 | 0 | 2024-11-13
BURHANPUR / KHAKNAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1747008065/WC/VB/22012035330423 — BOREWELL RECHARGE STRUCTURE PRIMARY SCHOOL KE PASS | Approved | 24122.63 | 0 | 2026-07-09
BURHANPUR / KHAKNAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1747008065/WC/VB/22012035330430 — BOREWELL RECHARGE STRUCTURE RAJKUMAR NANU KE GHAR KE PASS | Approved | 23855.69 | 0 | 2026-07-09
BURHANPUR / KHAKNAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1747008065/WC/VB/22012035330433 — BOREWELL RECHARGE STRUCTURE SUSHIL BHURA KE GHAR KE PASS | Approved | 22508.61 | 0 | 2026-07-09
BURHANPUR / KHAKNAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1747008065/WC/VB/22012035330435 — SOKPIT NIRMAN KARYA GRAM PANCHAYAT KE HANDPAMP KE PASS | Ongoing | 22781.21 | 0 | 2026-08-11
BURHANPUR / KHAKNAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1747008065/WC/VB/22012035330437 — SOKPIT NIRMAN KARYA HANUMAN MANDIR KE HANDPAMP KE PASS | Ongoing | 23048.29 | 0 | 2026-08-19
BURHANPUR / KHAKNAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1747008065/WC/VB/22012035330438 — SOKPIT NIRMAN KARYA MAHUPAL MANDIR KE HANDPAMP KE PASS | Approved | 24273.08 | 0 | 2026-06-05