## Work List
Exported on: 2026-10-17 20:27:44
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BORI BUZURG
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BURHANPUR / BURHANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/4531248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100605827 | Completed | 23490 | 0 | 2024-11-13 | 2026-08-29
BURHANPUR / BURHANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/4534162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102122986 | Completed | 23490 | 0 | 2025-02-25 | 2026-08-03
BURHANPUR / BURHANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/4536902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100757026 | Completed | 21870 | 0 | 2025-01-20 | 2026-08-03
BURHANPUR / BURHANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/4817910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100756933 | Completed | 23490 | 0 | 2025-08-13 | 2026-08-29
BURHANPUR / BURHANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/4831734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144099893 | Completed | 21870 | 0 | 2024-12-28 | 2026-08-03
BURHANPUR / BURHANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/4905797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100605835 | Completed | 27000 | 21600 | 2025-03-19 | 2026-10-12
BURHANPUR / BURHANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/4986406 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100758739 | Completed | 23490 | 0 | 2025-03-19 | 2026-08-03
BURHANPUR / BURHANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/4986838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100605596 | Completed | 23490 | 0 | 2025-03-19 | 2026-08-03
BURHANPUR / BURHANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5394006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120092891 | Completed | 27000 | 25200 | 2026-07-05 | 2026-10-12
BURHANPUR / BURHANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5411297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100645024 | Completed | 27000 | 3600 | 2025-11-11 | 2026-09-30
BURHANPUR / BURHANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5502478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100644407 | Completed | 23490 | 0 | 2025-06-17 | 2026-08-29
BURHANPUR / BURHANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5502479 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100644589 | Completed | 27000 | 24600 | 2026-07-05 | 2026-10-12
BURHANPUR / BURHANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5502570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100757932 | Completed | 23490 | 1800 | 2026-03-11 | 2026-08-29
BURHANPUR / BURHANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5502844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100605816 | Completed | 23490 | 0 | 2025-09-27 | 2026-08-29
BURHANPUR / BURHANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5502932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114833465 | Completed | 27000 | 0 | 2026-02-06 | 2026-09-18
BURHANPUR / BURHANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5583655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100756042 | Completed | 23490 | 0 | 2025-10-17 | 2026-08-29
BURHANPUR / BURHANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5590334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100832688 | Completed | 23490 | 3600 | 2025-08-03 | 2026-08-29
BURHANPUR / BURHANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5644737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100756000 | Completed | 23490 | 0 | 2026-05-13 | 2026-08-29
BURHANPUR / BURHANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5664197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100833328 | Completed | 23490 | 0 | 2025-09-18 | 2026-08-29
BURHANPUR / BURHANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5680867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100832052 | Completed | 23490 | 0 | 2025-08-31 | 2026-08-03
BURHANPUR / BURHANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5828689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100756648 | Completed | 23490 | 0 | 2025-09-27 | 2026-08-29
BURHANPUR / BURHANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5829609 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100758692 | Completed | 23490 | 3600 | 2025-11-20 | 2026-09-18
BURHANPUR / BURHANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5882834 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100841436 | Completed | 23490 | 1800 | 2026-05-23 | 2026-08-29
BURHANPUR / BURHANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5882965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105001311 | Completed | 27000 | 25200 | 2026-07-24 | 2026-10-12
BURHANPUR / BURHANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5883022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100644905 | Completed | 27000 | 25200 | 2026-07-24 | 2026-10-12
BURHANPUR / BURHANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5883171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114833985 | Completed | 27000 | 26400 | 2026-07-05 | 2026-10-12
BURHANPUR / BURHANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5883268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100757757 | Completed | 27000 | 27000 | 2026-07-05 | 2026-10-12
BURHANPUR / BURHANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5883320 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114833677 | Completed | 27000 | 27000 | 2026-07-03 | 2026-10-12
BURHANPUR / BURHANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5883479 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100756263 | Completed | 23490 | 1800 | 2026-04-12 | 2026-08-29
BURHANPUR / BURHANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5883607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100841412 | Completed | 27000 | 27000 | 2026-07-05 | 2026-10-12
BURHANPUR / BURHANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5883907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100583069 | Completed | 23490 | 0 | 2026-04-02 | 2026-08-03
BURHANPUR / BURHANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/5883958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142145953 | Completed | 27000 | 25200 | 2026-07-05 | 2026-09-30
BURHANPUR / BURHANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/6123347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120092861 | Completed | 27000 | 26400 | 2026-07-05 | 2026-10-12
BURHANPUR / BURHANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/6143611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104995606 | Completed | 23490 | 0 | 2026-05-03 | 2026-08-03
BURHANPUR / BURHANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/6164416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142480123 | Completed | 23490 | 1800 | 2026-05-19 | 2026-08-29
BURHANPUR / BURHANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1747009019/IF/IAY/6174556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104974755 | Completed | 23490 | 3600 | 2026-06-11 | 2026-08-29