## Work List
Exported on: 2026-10-25 12:51:54
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: AKHAIGHAT
Status: Physically Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ASHOK NAGAR / ISAGARH | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1748001008/AV/22012034662603 — egs shala adiwasi basti ke liye khel madan nirman akhaighat | Physically Completed | 478322.83 | 371341.6 | 2025-02-20 | 2026-04-08
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001008/IF/22012035067758 — PMAY SHIVLAL / BALDEVA JATAV | Physically Completed | 18360 | 17181 | 2023-07-10 | 2026-06-24
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1748001008/IF/22012035310464 — 1748001008/IF/22012035310464 | Physically Completed | 21870 | 19836 | 2025-05-27 | 2026-06-24
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1748001008/IF/22012035310465 — 1748001008/IF/22012035310465 | Physically Completed | 21870 | 21663 | 2025-05-27 | 2026-06-24
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1748001008/IF/22012035310466 — 1748001008/IF/22012035310466 | Physically Completed | 21870 | 19836 | 2025-05-27 | 2026-06-24
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1748001008/IF/22012035564368 — PMAYG PACHIYA BAI / BATRU JATAV | Physically Completed | 23490 | 22446 | 2025-10-12 | 2026-06-20
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1748001008/IF/22012035564391 — PMAY JAGDEESH / GHANSUNDAR MP100643462 | Physically Completed | 23490 | 13050 | 2025-08-12 | 2026-06-29
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001008/IF/IAY/4817179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100540036 | Physically Completed | 23490 | 21492 | 2025-02-14 | 2026-06-29
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001008/IF/IAY/5505209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105294299 | Physically Completed | 23490 | 15921 | 2025-05-03 | 2026-06-07