## Work List
Exported on: 2026-10-13 20:33:33
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BHARROLI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ASHOK NAGAR / ISAGARH | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1748001055/AV/22012034659146 — शांति धाम ग्राम कोठार खेड़ी ग्राम पंचायत भर्रोली | Approved | 229312.16 | 0 | 2024-05-27
ASHOK NAGAR / ISAGARH | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1748001055/AV/22012034662273 — Shanti Dham Talab ki par ke niche gram Bharroli | New | 0 | 0 | 2024-10-02
ASHOK NAGAR / ISAGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1748001055/DP/22012034601611 — अमृत वाटिका वृक्षारोपण शासकीय स्कूल परिसर भर्रौली | Ongoing | 55847.4 | 0 | 2023-10-06
ASHOK NAGAR / ISAGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/200892 — Construction of IAY House -IAY REG. NO. MP-48-001-055-003/36 | Approved | 27000 | 0 | 2016-03-10
ASHOK NAGAR / ISAGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/200893 — Construction of IAY House -IAY REG. NO. MP-48-001-055-003/40 | Approved | 27000 | 0 | 2016-03-10
ASHOK NAGAR / ISAGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/2143717 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5104053 | Approved | 27000 | 0 | 2019-06-22
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4364084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102386954 | Ongoing | 27000 | 0 | 2025-08-30
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4466975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151987593 | Ongoing | 27000 | 0 | 2025-12-14
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4466976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151987765 | Ongoing | 27000 | 0 | 2025-12-14
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4467479 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152010661 | Ongoing | 27000 | 0 | 2025-12-23
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4467504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013282 | Ongoing | 27000 | 0 | 2024-06-21
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4467505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013283 | Ongoing | 27000 | 0 | 2024-06-21
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4467506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013285 | Ongoing | 27000 | 0 | 2025-12-27
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4467836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152026316 | Ongoing | 27000 | 0 | 2024-06-21
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4468070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151986296 | Ongoing | 27000 | 0 | 2025-03-08
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4468363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151988345 | Ongoing | 27000 | 0 | 2024-06-21
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4468587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152030858 | Ongoing | 27000 | 0 | 2024-06-21
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4469694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013284 | Ongoing | 27000 | 0 | 2024-06-21
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4469695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013298 | Ongoing | 27000 | 0 | 2024-06-21
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4469697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013305 | Ongoing | 27000 | 0 | 2024-06-21
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4469698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013306 | Ongoing | 27000 | 0 | 2024-06-21
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4469699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013308 | Ongoing | 27000 | 0 | 2025-03-07
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4469700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013311 | Ongoing | 27000 | 1200 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4469705 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013327 | Ongoing | 27000 | 0 | 2025-08-30
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4469708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013339 | Ongoing | 27000 | 0 | 2024-06-21
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4469710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013347 | Ongoing | 27000 | 0 | 2025-09-25
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4469713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013355 | Ongoing | 27000 | 0 | 2024-12-10
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4469823 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152026317 | Ongoing | 27000 | 0 | 2024-06-21
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4469824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152026325 | Ongoing | 27000 | 0 | 2025-12-23
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4469949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151952464 | Ongoing | 27000 | 0 | 2024-06-21
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4470076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151985209 | Ongoing | 27000 | 0 | 2024-06-21
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4470199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151995179 | Ongoing | 27000 | 0 | 2025-12-14
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4470202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151995241 | Ongoing | 27000 | 0 | 2025-12-14
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4470208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151995321 | Ongoing | 27000 | 0 | 2024-06-21
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4470209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151995327 | Ongoing | 27000 | 0 | 2024-06-21
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4470210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151995373 | Ongoing | 27000 | 0 | 2024-06-21
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4470214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151995424 | Ongoing | 27000 | 0 | 2025-12-27
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032863 | Physically Completed | 23490 | 0 | 2025-02-17 | 2026-08-16
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032864 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032865 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032866 | Ongoing | 27000 | 0 | 2025-03-07
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032867 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032868 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032869 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032871 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032872 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032873 | Ongoing | 27000 | 0 | 2025-03-07
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508372 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032874 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508373 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032875 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508374 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032876 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032879 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032880 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032882 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032884 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508380 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032887 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032889 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032890 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032891 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032937 | Ongoing | 27000 | 0 | 2025-03-07
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032939 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032941 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032944 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032946 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032947 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4508391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032964 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4509244 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013280 | Ongoing | 27000 | 0 | 2025-03-07
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4509858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151995410 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4510114 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032877 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4510115 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032883 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4510116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032942 | Ongoing | 27000 | 0 | 2025-02-17
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4512884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032949 | Physically Completed | 23490 | 0 | 2025-03-07 | 2026-08-16
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4533814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100903245 | Physically Completed | 23490 | 0 | 2025-05-03 | 2026-08-16
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4541689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104989869 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4684009 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102665123 | Ongoing | 27000 | 0 | 2025-02-09
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4685912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102387164 | Ongoing | 27000 | 1500 | 2025-02-09
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/4841422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032878 | Ongoing | 27000 | 0 | 2025-03-07
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5482551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102665620 | Ongoing | 27000 | 7200 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5482555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102680104 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5482557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102680207 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5482597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102668410 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5482600 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102674889 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5482601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102676097 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5482602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102676352 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5482691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102267063 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5482841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102386385 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5483010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104986947 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5483218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102387449 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5483219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102387823 | Physically Completed | 23490 | 0 | 2025-05-03 | 2026-07-19
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5483220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102387900 | Physically Completed | 27000 | 7200 | 2025-05-03 | 2026-10-11
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5483333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104986662 | Ongoing | 27000 | 7200 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5483426 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104985851 | Physically Completed | 23490 | 600 | 2025-05-03 | 2026-08-09
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5483459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100903849 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5483463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100905143 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5483778 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105852535 | Ongoing | 27000 | 7200 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5484019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100904165 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5484023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102673690 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5484024 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102674051 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5484459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105863866 | Ongoing | 27000 | 0 | 2025-08-28
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5484945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102388039 | Physically Completed | 27000 | 3600 | 2025-05-03 | 2026-09-20
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5484946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102388110 | Physically Completed | 27000 | 3600 | 2025-05-03 | 2026-09-20
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5484947 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102388161 | Ongoing | 27000 | 3600 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5484948 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102388206 | Ongoing | 27000 | 1800 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5484951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102388342 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5484967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102674213 | Ongoing | 27000 | 1800 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5484968 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102674404 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5485381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105864718 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5485912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102666436 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5486250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105833815 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5486362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104990257 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5486443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102680554 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5486575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100904916 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5486576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102386444 | Physically Completed | 23490 | 0 | 2025-05-03 | 2026-07-26
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5486578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102386629 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5486579 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102386778 | Physically Completed | 23490 | 0 | 2025-05-03 | 2026-07-26
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5486668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102670564 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5486761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102678000 | Physically Completed | 27000 | 0 | 2025-05-03 | 2026-08-30
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5486762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102675862 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5486766 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102679202 | Physically Completed | 27000 | 0 | 2025-05-03 | 2026-10-11
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5486767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102679346 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5518577 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100903596 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5519808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102672652 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5520879 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102664482 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5522697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104987590 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5526357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102667687 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5526578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102676655 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5527416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102678667 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5527417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102679895 | Physically Completed | 27000 | 6900 | 2025-05-03 | 2026-10-11
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5528018 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100904013 | Physically Completed | 27000 | 0 | 2025-05-03 | 2026-10-11
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5528759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102674585 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5530721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102387051 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5530827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102677809 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5530828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102675666 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5530829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102679015 | Ongoing | 27000 | 0 | 2025-05-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5664449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076772 | Ongoing | 27000 | 4200 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5664498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076783 | Ongoing | 27000 | 4200 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5664543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076776 | Ongoing | 27000 | 3600 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5664591 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076780 | Ongoing | 27000 | 0 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5664592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076823 | Physically Completed | 27000 | 0 | 2025-08-03 | 2026-09-27
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5664638 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076766 | Ongoing | 27000 | 0 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5664685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076768 | Ongoing | 27000 | 0 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5664826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076764 | Ongoing | 27000 | 0 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5664827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076809 | Ongoing | 27000 | 3600 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5664937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076911 | Ongoing | 27000 | 0 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5665163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076914 | Ongoing | 27000 | 0 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5665237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076904 | Ongoing | 27000 | 3600 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5665338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076799 | Ongoing | 27000 | 0 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5665381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076778 | Ongoing | 27000 | 3600 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5665430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076815 | Physically Completed | 27000 | 3000 | 2025-08-03 | 2026-09-27
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5665478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076797 | Ongoing | 27000 | 0 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5665524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076781 | Ongoing | 27000 | 0 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5665941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076908 | Ongoing | 27000 | 0 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5708363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102665367 | Ongoing | 27000 | 7200 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5709009 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104988909 | Ongoing | 27000 | 0 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5709171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102680843 | Ongoing | 27000 | 0 | 2025-08-03
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5974038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102682093 | Ongoing | 27000 | 19800 | 2026-06-04
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5974039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102682199 | Ongoing | 27000 | 0 | 2026-06-04
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5974192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102681627 | Ongoing | 27000 | 0 | 2026-05-19
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5974231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102387109 | Ongoing | 27000 | 16200 | 2026-04-09
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5974232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102387679 | Ongoing | 27000 | 16200 | 2026-06-04
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5974233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102387783 | Ongoing | 27000 | 19800 | 2026-05-19
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5974234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102387939 | Ongoing | 27000 | 19800 | 2026-05-19
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5974307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100903731 | Ongoing | 27000 | 19800 | 2026-05-20
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5974308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100904241 | Ongoing | 27000 | 19800 | 2026-05-19
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5974508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104987845 | Ongoing | 27000 | 0 | 2026-05-19
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5974843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104985486 | Ongoing | 27000 | 7200 | 2026-05-20
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5975155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100903396 | Ongoing | 27000 | 3600 | 2026-05-19
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5975156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100903543 | Ongoing | 27000 | 16200 | 2026-05-27
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5975315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100902808 | Ongoing | 27000 | 15900 | 2026-05-20
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5975316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100902993 | Ongoing | 27000 | 10800 | 2026-08-15
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5975423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102669409 | Ongoing | 27000 | 14400 | 2026-07-21
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5975424 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102386706 | Ongoing | 27000 | 10800 | 2026-06-04
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5975426 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102387389 | Ongoing | 27000 | 0 | 2026-05-19
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5975427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102387525 | Ongoing | 27000 | 10800 | 2026-05-19
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/5975428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102387640 | Ongoing | 27000 | 0 | 2026-05-19
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/6309108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100902927 | Approved | 27000 | 0 | 2026-02-17
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/6309171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102388277 | Approved | 27000 | 0 | 2026-02-17
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/6309351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102387343 | Ongoing | 27000 | 0 | 2026-10-08
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/6309353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102387869 | Ongoing | 27000 | 0 | 2026-10-08
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/6314590 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102387589 | Approved | 27000 | 0 | 2026-02-17
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/6318287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100903132 | Ongoing | 27000 | 0 | 2026-10-08
ASHOK NAGAR / ISAGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/6318300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100902671 | Ongoing | 27000 | 0 | 2026-10-08
ASHOK NAGAR / ISAGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/63952 — Construction of IAY House -IAY REG. NO. MP-48-001-055-002/126 | Approved | 27000 | 0 | 2015-12-30
ASHOK NAGAR / ISAGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/63955 — Construction of IAY House -IAY REG. NO. MP-48-001-055-002/13 | Approved | 27000 | 0 | 2015-12-30
ASHOK NAGAR / ISAGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748001055/IF/IAY/86152 — Construction of IAY House -IAY REG. NO. MP-48-001-055-003/15 | Approved | 27000 | 0 | 2016-01-13
ASHOK NAGAR / ISAGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1748001055/WC/22012034550437 — Chek Dam Nirman Nahar k pass serve NO.134 | Ongoing | 314518.84 | 0 | 2020-08-15
ASHOK NAGAR / ISAGARH | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1748/RC/22012034615957 — Maintenance of CMGSY Road Bharroli Ajleshwar Road se Mindpura | Ongoing | 341000 | 0 | 2023-02-18