## Work List
Exported on: 2026-09-14 06:48:55
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: SHRIANANDPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ASHOK NAGAR / ISAGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1748001072/AV/22012034510987 — Shantidham Prangan mi Boundrywall Nirman Naithai | Completed | 75000 | 59660 | 2020-07-03 | 2021-02-25
ASHOK NAGAR / ISAGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1748001072/AV/22012034538635 — Samudayak Swachhta Parishar Shantidham ke pass Naithai | Completed | 86000 | 40704 | 2020-11-27 | 2024-09-10
ASHOK NAGAR / ISAGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1748001072/AV/22012034602663 — डाइनिंग टेबल अरेंजमेंट पीएस स्कूल नेथाई | Closed | 0 | 0 | 2021-10-02
ASHOK NAGAR / ISAGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1748001072/AV/22012034615471 — estimate for construction maa ki bagiya P S School nathai | Closed | 0 | 0 | 2022-01-26
ASHOK NAGAR / ISAGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1748001072/DP/22012034598536 — amart vatika nirman school prangn gram naithai gram panchayt shri anandpur | Closed | 0 | 0 | 2023-08-07
ASHOK NAGAR / ISAGARH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1748001072/IF/22012034354011 — hitesh khettalab karan singh S/o bhagchandr | Completed | 33000 | 18414 | 2018-07-07 | 2020-07-30
ASHOK NAGAR / ISAGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748001072/IF/22012034356313 — khet talab kapori bai w/o surat singh | Completed | 102000 | 88256 | 2017-07-08 | 2020-06-11
ASHOK NAGAR / ISAGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1748001072/IF/22012034359954 — plantation main road se said ki orgram natathai | Completed | 335000 | 30960 | 2017-07-01 | 2020-09-25
ASHOK NAGAR / ISAGARH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1748001072/IF/22012034362825 — hiteshi khet talab babulal s/o bhagchandr | Completed | 33000 | 31932 | 2018-06-10 | 2020-06-13
ASHOK NAGAR / ISAGARH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1748001072/IF/22012034362828 — comunity plantation school and mata mandir | Ongoing | 544000 | 77341 | 2018-08-07
ASHOK NAGAR / ISAGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748001072/IF/22012034362830 — खेत तालब निर्माण भागो बाई पति मिश्री लाल | Completed | 33000 | 10630 | 2018-06-02 | 2020-06-11
ASHOK NAGAR / ISAGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748001072/IF/22012034420376 — Khket talab kamlsingh s/o kashiram | Completed | 33000 | 19644 | 2018-06-23 | 2020-06-11
ASHOK NAGAR / ISAGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748001072/IF/22012034420378 — Khket talab mushilal s/o bhabut singh | Completed | 33000 | 25260 | 2018-06-23 | 2020-06-11
ASHOK NAGAR / ISAGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748001072/IF/22012034420383 — Khket talab lalajiram s/o kapoora | Completed | 33000 | 13094 | 2018-06-23 | 2020-06-11
ASHOK NAGAR / ISAGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748001072/IF/22012034421008 — khet talab bhagawan singh s/o malam singh | Completed | 33000 | 19348 | 2018-06-23 | 2020-06-11
ASHOK NAGAR / ISAGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748001072/IF/22012034484233 — खेत तालाब निर्माण राम सिंह पुत्र सोहन सिंह | Closed | 0 | 0 | 2019-06-01
ASHOK NAGAR / ISAGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Raising of Nursery for Individuals / Raising of Nursery for Individuals | Nursery Development | 1748001072/IF/22012034501183 — nadiv nirmad gajaraj singh | Closed | 0 | 0 | 2019-08-16
ASHOK NAGAR / ISAGARH | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1748001072/IF/22012034501184 — nadiv nirmad naini bai | Closed | 0 | 0 | 2019-08-16
ASHOK NAGAR / ISAGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1748001072/IF/22012034579579 — nandan phalodyaan yojana SHRI KUMAR BAI /PHALWAN SINGH | Closed | 0 | 0 | 2020-06-20
ASHOK NAGAR / ISAGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1748001072/IF/22012034579581 — nandan phalodyaan yojana bhago bai /misharilala | Ongoing | 135219.86 | 5650.8 | 2020-07-08
ASHOK NAGAR / ISAGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1748001072/IF/22012034579781 — nandan phalodyaan yojana shri kumar bai /pahalwan singh | Ongoing | 135219.86 | 12419 | 2020-07-02
ASHOK NAGAR / ISAGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1748001072/IF/22012034581765 — NADAN PHALUDYAN MANAA BAI /LALJIRAM | Closed | 0 | 0 | 2020-06-20
ASHOK NAGAR / ISAGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1748001072/IF/22012034581766 — NANDAN PHALUDYAN RAJ BAI KMMU | Closed | 0 | 0 | 2020-06-20
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1748001072/IF/22012035615320 — ek bagiya maa ke nam hiriya kushwah | New | 0 | 0 | 2025-08-15
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1748001072/IF/22012035615321 — ek bagiya maa ke nam hiriya kushwah | Approved | 0 | 0 | 2025-08-15
ASHOK NAGAR / ISAGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1748001072/IF/22012035633178 — EK BAGIYA MAA KE NAAM HIRIYA BAI/ NARAYAN SINGH GRAM NAITHAI | Ongoing | 266578.64 | 1044 | 2026-01-13
ASHOK NAGAR / ISAGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/119535 — Construction of IAY House -IAY REG. NO. MP-48-001-072-002/1 | Completed | 14310 | 13861 | 2016-12-03 | 2017-03-31
ASHOK NAGAR / ISAGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/119536 — Construction of IAY House -IAY REG. NO. MP-48-001-072-002/2 | Completed | 14310 | 12859 | 2016-12-03 | 2017-03-08
ASHOK NAGAR / ISAGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/2149154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5245848 | Completed | 15840 | 14956 | 2019-07-08 | 2020-05-30
ASHOK NAGAR / ISAGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/2166644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5688894 | Completed | 15840 | 15840 | 2019-07-08 | 2020-03-31
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3674126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105846451 | Completed | 18360 | 18173 | 2022-09-14 | 2024-01-18
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3791481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100781272 | Completed | 18360 | 17544 | 2022-06-04 | 2023-02-26
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3791482 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100781280 | Completed | 18360 | 18224 | 2022-11-05 | 2024-01-18
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3794757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103436064 | Completed | 18360 | 18156 | 2022-06-04 | 2024-01-18
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3795638 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105849585 | Completed | 18360 | 18210 | 2023-07-13 | 2024-08-02
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3807334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105402895 | Completed | 18360 | 18241 | 2022-07-07 | 2023-08-28
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3807341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105406859 | Completed | 18360 | 18224 | 2022-07-21 | 2024-01-18
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3807345 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105407712 | Completed | 18360 | 18224 | 2022-07-21 | 2024-01-18
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3807347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105407987 | Completed | 18360 | 18210 | 2023-07-13 | 2024-08-03
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3807351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105409609 | Completed | 18360 | 18266 | 2022-07-21 | 2024-08-26
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3807355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105413229 | Completed | 18360 | 17748 | 2022-08-18 | 2024-08-03
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3807372 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105416611 | Completed | 18360 | 18309 | 2022-08-18 | 2024-08-26
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3807405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105427650 | Completed | 18360 | 18156 | 2022-12-18 | 2024-08-05
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3807412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105430741 | Physically Completed | 18360 | 18210 | 2023-07-13 | 2024-11-28
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3919422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105089076 | Completed | 18360 | 17748 | 2022-06-04 | 2024-08-05
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105407333 | Completed | 18360 | 18120 | 2023-12-17 | 2024-11-23
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105408908 | Completed | 18360 | 17973 | 2022-08-18 | 2024-08-04
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105410282 | Completed | 18360 | 17148 | 2023-07-05 | 2024-11-23
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105411966 | Completed | 18360 | 18030 | 2022-08-18 | 2024-08-26
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922661 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105412436 | Completed | 18360 | 17493 | 2022-08-18 | 2024-08-28
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105413616 | Completed | 18360 | 18231 | 2023-12-05 | 2024-08-26
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105414005 | Completed | 18360 | 17238 | 2022-07-15 | 2024-08-28
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105414335 | Completed | 18360 | 17502 | 2024-01-08 | 2024-11-23
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105415437 | Physically Completed | 18360 | 15504 | 2022-08-18 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105416224 | Completed | 18360 | 18241 | 2022-07-21 | 2024-01-18
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105417156 | Physically Completed | 18360 | 18120 | 2023-10-03 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105421427 | Completed | 18360 | 18342 | 2023-08-23 | 2024-11-23
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105424660 | Completed | 18360 | 18030 | 2022-08-18 | 2024-08-26
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105428004 | Completed | 18360 | 17622 | 2022-11-05 | 2024-08-28
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105429932 | Completed | 18360 | 18231 | 2024-01-08 | 2024-08-26
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105430427 | Completed | 18360 | 18231 | 2024-01-08 | 2024-09-10
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922686 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105431871 | Physically Completed | 18360 | 17370 | 2024-01-08 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922687 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105432397 | Completed | 18360 | 18312 | 2022-07-21 | 2024-08-28
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3922693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105436720 | Physically Completed | 18360 | 16884 | 2023-08-23 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3923268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100586840 | Physically Completed | 18360 | 11601 | 2024-01-08 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3923271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100587120 | Physically Completed | 18360 | 16856 | 2022-07-21 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3923285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100590771 | Physically Completed | 18360 | 18054 | 2022-12-18 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3923288 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100591004 | Completed | 18360 | 17604 | 2022-11-05 | 2024-11-23
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3923289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100591469 | Physically Completed | 18360 | 16856 | 2022-07-21 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3923290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100591536 | Completed | 18360 | 16728 | 2022-07-21 | 2024-09-07
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3923291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100591565 | Physically Completed | 18360 | 14688 | 2022-07-15 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3923293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100591799 | Physically Completed | 18360 | 13809 | 2023-11-02 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3923294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100591847 | Physically Completed | 18360 | 12222 | 2022-11-05 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3925238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105440622 | Physically Completed | 18360 | 17010 | 2024-04-20 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3925241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105441357 | Physically Completed | 18360 | 17982 | 2024-05-11 | 2024-11-28
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3925327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105526644 | Completed | 18360 | 17550 | 2022-08-18 | 2024-11-23
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3927317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102949637 | Physically Completed | 18360 | 13788 | 2023-08-26 | 2024-11-28
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3927448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103436760 | Completed | 18360 | 17136 | 2022-07-15 | 2024-09-10
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3927450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103437587 | Completed | 18360 | 18342 | 2023-07-22 | 2024-11-23
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3927458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103440076 | Completed | 18360 | 18342 | 2022-07-07 | 2024-09-10
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3927459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103440509 | Completed | 18360 | 18069 | 2022-07-15 | 2024-09-10
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3928474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106443819 | Physically Completed | 18360 | 5304 | 2023-12-05 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3931890 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105840854 | Completed | 18360 | 17826 | 2022-06-04 | 2024-09-07
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3931894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105843002 | Physically Completed | 18360 | 12636 | 2024-05-11 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3931895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105843269 | Completed | 18360 | 17856 | 2022-07-07 | 2024-11-23
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3931897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105843573 | Closed | 18360 | 0 | 2022-05-08
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3931899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105844463 | Physically Completed | 18360 | 15470 | 2023-10-03 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3931905 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105846309 | Physically Completed | 18360 | 18234 | 2022-12-18 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3931906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105846344 | Physically Completed | 18360 | 17370 | 2023-07-22 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3931907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105846402 | Completed | 18360 | 18343 | 2023-09-12 | 2024-09-10
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3931920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105850132 | Physically Completed | 18360 | 11736 | 2022-12-18 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3931921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105850243 | Physically Completed | 18360 | 17496 | 2024-04-20 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3931923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105852202 | Physically Completed | 18360 | 12648 | 2023-01-30 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3932329 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100930741 | Completed | 18360 | 16728 | 2022-06-04 | 2024-09-07
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3934284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104909162 | Completed | 18360 | 15402 | 2022-07-15 | 2024-10-14
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3935492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102162263 | Physically Completed | 18360 | 10260 | 2022-11-19 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3938031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104969722 | Completed | 18360 | 18360 | 2022-09-10 | 2023-03-27
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3949150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144599690 | Completed | 18360 | 18122 | 2023-11-02 | 2024-09-07
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3994069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103436339 | Physically Completed | 18360 | 7956 | 2024-03-14 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3994076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103437955 | Completed | 18360 | 18343 | 2023-07-22 | 2024-09-10
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3994077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103438487 | Physically Completed | 18360 | 3645 | 2024-07-03 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3994079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103439329 | Physically Completed | 18360 | 13668 | 2022-07-07 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3994080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103439879 | Physically Completed | 18360 | 14688 | 2022-11-29 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3994271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100781289 | Completed | 18360 | 18360 | 2022-07-15 | 2023-03-27
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3994452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100929701 | Completed | 18360 | 18210 | 2023-08-07 | 2024-11-23
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3994711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105848965 | Physically Completed | 18360 | 17496 | 2024-04-20 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3994712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105850030 | Physically Completed | 18360 | 14688 | 2022-11-29 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3994713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105850504 | Physically Completed | 18360 | 12444 | 2022-08-18 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3994714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105850938 | Physically Completed | 18360 | 13260 | 2022-09-14 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3994715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105851312 | Completed | 18360 | 18224 | 2022-08-18 | 2024-01-18
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3994716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105851749 | Physically Completed | 18360 | 11526 | 2022-12-18 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3994730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105865287 | Physically Completed | 18360 | 11934 | 2023-07-25 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3995100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105268966 | Completed | 18360 | 17748 | 2022-08-18 | 2024-09-10
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3995232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105403846 | Completed | 18360 | 18360 | 2022-07-21 | 2023-03-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3995233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105404462 | Physically Completed | 18360 | 11118 | 2022-07-21 | 2024-11-28
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3995235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105405211 | Completed | 18360 | 18360 | 2022-07-21 | 2023-02-26
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3995237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105409140 | Physically Completed | 18360 | 7548 | 2022-11-29 | 2024-11-28
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3995240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105410491 | Completed | 18360 | 18360 | 2022-07-21 | 2023-03-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3995292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100591495 | Physically Completed | 18360 | 12444 | 2023-01-30 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3995294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100591615 | Physically Completed | 18360 | 9900 | 2023-04-11 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3995298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100593295 | Completed | 18360 | 18138 | 2023-01-30 | 2024-11-23
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3995862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105996038 | Completed | 18360 | 17748 | 2022-11-05 | 2024-09-10
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3995864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105996193 | Physically Completed | 18360 | 11832 | 2023-01-30 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3997130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104910241 | Physically Completed | 18360 | 17370 | 2023-04-11 | 2024-11-28
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3997132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104911906 | Physically Completed | 18360 | 14540 | 2023-04-11 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3997157 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104932666 | Physically Completed | 18360 | 16244 | 2022-12-18 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3997197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104951281 | Physically Completed | 18360 | 18167 | 2022-07-07 | 2024-12-11
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3997791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106290831 | Physically Completed | 18360 | 13608 | 2024-07-03 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105410657 | Physically Completed | 18360 | 9699 | 2023-07-23 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105414744 | Completed | 18360 | 18315 | 2022-08-18 | 2024-11-23
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105415072 | Completed | 18360 | 18069 | 2022-07-07 | 2024-11-23
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105419830 | Completed | 18360 | 18177 | 2022-07-21 | 2024-11-23
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105420273 | Physically Completed | 18360 | 4896 | 2022-11-11 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105421083 | Physically Completed | 18360 | 17166 | 2022-12-18 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105423297 | Completed | 18360 | 18156 | 2022-12-18 | 2024-09-10
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105424044 | Completed | 18360 | 18273 | 2022-12-11 | 2024-11-23
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105425219 | Physically Completed | 18360 | 8652 | 2022-12-11 | 2024-11-28
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105428642 | Completed | 23490 | 17955 | 2022-08-18 | 2025-05-20
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105431109 | Completed | 18360 | 18234 | 2022-08-18 | 2024-09-07
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105431599 | Completed | 18360 | 18360 | 2022-12-18 | 2023-03-27
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105436132 | Physically Completed | 18360 | 16482 | 2023-08-23 | 2024-11-28
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105437822 | Completed | 18360 | 18360 | 2022-07-21 | 2023-03-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105440992 | Completed | 18360 | 18234 | 2022-12-18 | 2024-09-10
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105444797 | Completed | 18360 | 18054 | 2023-01-13 | 2023-08-25
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102949350 | Completed | 18360 | 17622 | 2023-01-13 | 2024-09-10
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998627 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102949539 | Completed | 18360 | 18360 | 2022-08-18 | 2023-03-26
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/3998629 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102949776 | Completed | 18360 | 18156 | 2023-01-30 | 2024-08-04
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/4003445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113691441 | Completed | 18360 | 18360 | 2022-11-11 | 2023-03-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/4056192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100591725 | Completed | 18360 | 18342 | 2022-07-07 | 2024-11-23
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/4114613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105846985 | Completed | 18360 | 17826 | 2022-07-15 | 2024-09-10
ASHOK NAGAR / ISAGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/4114624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105861547 | Physically Completed | 18360 | 18120 | 2023-08-07 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/4117397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105411718 | Completed | 18360 | 17952 | 2023-01-30 | 2024-08-04
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/4117398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105412912 | Completed | 18360 | 17748 | 2023-01-30 | 2024-09-10
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/4117409 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105517241 | Completed | 18360 | 17952 | 2023-01-30 | 2024-08-04
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/4373722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102997587 | Completed | 18360 | 18360 | 2023-01-30 | 2024-08-04
ASHOK NAGAR / ISAGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/4388815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105429111 | Completed | 18360 | 17928 | 2023-01-30 | 2024-09-07
ASHOK NAGAR / ISAGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/4411548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105438536 | Physically Completed | 19890 | 8748 | 2024-10-15 | 2024-11-27
ASHOK NAGAR / ISAGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748001072/IF/IAY/580744 — Construction of IAY House -IAY REG. NO. MP3600048 | Completed | 15030 | 15923 | 2017-01-28 | 2018-01-02
ASHOK NAGAR / ISAGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1748001072/LD/22012034295170 — Shati Dham niramad nathai | Completed | 180000 | 179080 | 2016-12-25 | 2017-07-15
ASHOK NAGAR / ISAGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1748001072/LD/22012034517093 — MED BADHAN DIMAN /OMKARLALA | Closed | 0 | 0 | 2020-05-15
ASHOK NAGAR / ISAGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1748001072/LD/22012034517094 — MED BABULALA /BHAGACHAND | Closed | 0 | 0 | 2020-05-14
ASHOK NAGAR / ISAGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1748001072/LD/22012034517095 — MED BANDAN MHARAJ SINGH | Closed | 0 | 0 | 2020-05-14
ASHOK NAGAR / ISAGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1748001072/LD/22012034517096 — MED KAPOORI BAI | Closed | 0 | 0 | 2020-05-14
ASHOK NAGAR / ISAGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1748001072/LD/22012034543160 — PALY GROUND PS SCHOOL PARISHAR NETHAI | Closed | 0 | 0 | 2021-01-26
ASHOK NAGAR / ISAGARH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1748001072/LD/3799395862 — MED NARAYAN SINGH/ SURATIYA | Completed | 27000 | 23652 | 2013-06-15 | 2013-06-28
ASHOK NAGAR / ISAGARH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1748001072/LD/3799395864 — MED TULSERAM / GEDALAL | Completed | 27000 | 24528 | 2013-06-15 | 2013-06-28
ASHOK NAGAR / ISAGARH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1748001072/LD/3799395865 — MED ARJUN / LAXMAN | Completed | 27000 | 23652 | 2013-06-15 | 2013-07-30
ASHOK NAGAR / ISAGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1748001072/PG/22012034305294 — Khail maidan nathai | Deleted | 353000 | 0 | 2017-04-25
ASHOK NAGAR / ISAGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1748001072/RC/22012034196769 — c.c.kharaja naithai | Completed | 126000 | 118938 | 2013-12-31 | 2014-03-26
ASHOK NAGAR / ISAGARH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1748001072/RC/22012034222381 — cc kharan brjesh keghr se ramjanki aashram ki or | Completed | 350000 | 244594 | 2014-06-20 | 2016-08-10
ASHOK NAGAR / ISAGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1748001072/RC/22012034288277 — CC ROAD | Completed | 95000 | 95400 | 2015-11-20 | 2016-09-06
ASHOK NAGAR / ISAGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1748001072/RC/22012034316785 — c.c.road kalyan kushwah ke ghar se surendr ke ghar ki or bhag 2 | Completed | 99000 | 98864 | 2016-11-26 | 2017-03-16
ASHOK NAGAR / ISAGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1748001072/RC/22012034323241 — c c road kishan ke ghar se meharwan ke makan ki or | Deleted | 0 | 0 | 2017-04-01
ASHOK NAGAR / ISAGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1748001072/RC/22012034323797 — c. c. road balls se mai road tak | Deleted | 0 | 0 | 2017-04-01
ASHOK NAGAR / ISAGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1748001072/RC/22012034334847 — sudur samark sadak garm nathai se delkawar ki or | Deleted | 1300000 | 0 | 2017-09-16
ASHOK NAGAR / ISAGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1748001072/RC/22012034373445 — SUDUR SADAK SHRIAANANDPUR | Closed | 0 | 0 | 2017-10-20
ASHOK NAGAR / ISAGARH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1748001072/RC/22012034508009 — Cc Road Itwari Balmiki Ke Ghar Se Shantidham Ki Or Gram Naithai | Closed | 28000 | 0 | 2019-08-15
ASHOK NAGAR / ISAGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1748001072/RC/22012034524803 — NALI NIRMAN VIKARAM SINGH KE GHAR SE NATHAI NALE TAK | Closed | 0 | 0 | 2020-05-14
ASHOK NAGAR / ISAGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1748001072/RC/22012034524838 — c.c.road mansingh ke ghar se main road ki or | Closed | 0 | 0 | 2020-05-14
ASHOK NAGAR / ISAGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1748001072/RC/22012034525323 — CC sadak Nirman Itbari Balmik k ghar se shantidham ki or | Completed | 29000 | 36480 | 2020-06-12 | 2020-08-15
ASHOK NAGAR / ISAGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1748001072/RC/22012034531589 — Nali Nirman Vikram singh kushwah k makan se Nale tak dono orse | Completed | 31000 | 18387 | 2020-08-27 | 2021-07-17
ASHOK NAGAR / ISAGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1748001072/RC/22012034531590 — CC sadak Nirman Mansingh k makan se Muram road tak | Completed | 58000 | 34337 | 2020-09-23 | 2021-08-25
ASHOK NAGAR / ISAGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1748001072/RC/22012034605582 — approach Road raod nirman naithai se selkawar ki or | Closed | 0 | 0 | 2022-01-25
ASHOK NAGAR / ISAGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1748001072/RC/22012034605583 — approach Road raod nirman naithai se selkawar ki or | Closed | 0 | 0 | 2022-01-31
ASHOK NAGAR / ISAGARH | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1748001072/RC/22012034623342 — CC and drain construction community building towards the hanuman ji temple nathai and chhok | Closed | 99000 | 0 | 2022-11-20
ASHOK NAGAR / ISAGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1748001072/RC/22012034644185 — CC ROAD AND NALI NIRMAN KARYA SAMUDAYAK BHAVAN SE MANDIR KI OR AVAM CHOCK MI GRAM NAITHAI | Ongoing | 99000 | 7530 | 2023-09-10
ASHOK NAGAR / ISAGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1748001072/RS/28786 — mariyada abhiyan brijesh / komal | Completed | 9900 | 4370 | 2013-06-05 | 2013-06-29
ASHOK NAGAR / ISAGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1748001072/RS/40697 — maryadh abhiyan bhagavansingh/ ram singh nayak | Completed | 9900 | 4370 | 2013-07-01 | 2013-11-01
ASHOK NAGAR / ISAGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1748001072/RS/40704 — maryda abhyan lakhan/ramsingh nayak | Completed | 9900 | 4370 | 2013-07-01 | 2013-11-01
ASHOK NAGAR / ISAGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1748001072/RS/40716 — maryad abhyan ashokkumar/pahalwan kushwah | Completed | 9900 | 2920 | 2013-11-30 | 2014-01-30
ASHOK NAGAR / ISAGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1748001072/RS/40720 — maryad abhyan kamalsinghiramsingh nayak | Completed | 9900 | 4370 | 2013-11-04 | 2014-01-20
ASHOK NAGAR / ISAGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1748001072/RS/40721 — maryad abhyan bhayalal/ramsingh nayak | Completed | 9900 | 2920 | 2013-11-30 | 2014-01-20
ASHOK NAGAR / ISAGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1748001072/RS/40723 — maryad abhyan surat singh/ramsingh nayk | Completed | 9900 | 2920 | 2013-11-30 | 2014-02-01
ASHOK NAGAR / ISAGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1748001072/RS/40725 — maryad abhyan laxmad /ramsingh nayak | Completed | 9900 | 4370 | 2013-07-01 | 2013-08-01
ASHOK NAGAR / ISAGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1748001072/RS/40727 — maryad abhyan abhay singh/ram singh nayak | Completed | 9900 | 2920 | 2013-07-01 | 2013-08-01
ASHOK NAGAR / ISAGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1748001072/RS/40728 — maryad abhyan bahadursingh/narayan singh kushwah | Completed | 9900 | 2920 | 2013-07-01 | 2013-08-01
ASHOK NAGAR / ISAGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1748001072/RS/40729 — maryad abhyan vimal/badri prasad kushwah | Completed | 9900 | 2920 | 2013-07-01 | 2013-08-01
ASHOK NAGAR / ISAGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1748001072/RS/84570 — NBA DIMAN/RAMSINGH NAYAK | Completed | 4400 | 4370 | 2013-07-06 | 2014-01-10
ASHOK NAGAR / ISAGARH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1748001072/WC/22012034435857 — bori bandhan | Closed | 0 | 0 | 2018-10-02
ASHOK NAGAR / ISAGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1748001072/WH/22012034931509 — Check Dem Jiddhodhar Karya Anandpur boundry ke pichhe garm Naithai | Closed | 0 | 0 | 2022-04-04