## Work List
Exported on: 2026-10-05 18:14:09
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: NAGESHRI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1748005041/IC/22012034889595 — सार्वजनिक कूप निर्माण शाला भवन के पास नगेश्री | New | 0 | 0 | 2025-01-24
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1748005041/IC/22012034889596 — सार्वजनिक कूप निर्माण पुराने प्राथमिक शाला भवन के पास इंगलेखेड़ी | New | 0 | 0 | 2025-01-25
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1748005041/IC/22012034889994 — सार्वजनिक कूप निर्माण शाला भवन के पास नगेश्री | Approved | 605674.76 | 0 | 2025-04-01
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1748005041/IC/22012034889995 — सार्वजनिक कूप निर्माण शाला भवन के पास इंगलेखेड़ी | Approved | 605674.76 | 0 | 2025-04-01
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005041/IF/22012035283952 — Kapildhara Koop Nirman Laxmi Bai /Keerat Singh Dangi Bamuriyadangi | Ongoing | 259004.76 | 0 | 2025-03-12
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005041/IF/22012035314459 — कपिलधारा कूप निर्माण तुलसीराम /गयारसा अहिरवार | Approved | 267533.14 | 0 | 2025-01-28
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005041/IF/22012035314490 — कपिलधारा कूप निर्माण मनोहर /विजय सिंह बमुरिया दांगी | Approved | 267533.14 | 0 | 2025-01-27
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005041/IF/22012035314517 — कपिलधारा कूप निर्माण मुन्ना / सूरत सिंह नगेश्री | Ongoing | 387700.4 | 0 | 2025-06-04
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005041/IF/22012035315321 — कपिलधारा कूप निर्माण पुष्पा बाई / पहलवान दांगी | Approved | 0 | 0 | 2025-01-27
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005041/IF/22012035315333 — कपिलधारा कूप निर्माण करन सिंह /गप्पु अहिरवार | Approved | 0 | 0 | 2025-01-24
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005041/IF/22012035325827 — कपिलधारा कूप निर्माण पुष्पा बाई /पहलवान दांगी | Approved | 267533.14 | 0 | 2025-04-02
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005041/IF/22012035325835 — कपिलधारा कूप निर्माण करन सिंह /गप्पू | Approved | 267533.14 | 0 | 2025-04-05
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005041/IF/22012035505839 — Kapildhara Koop Nirman Sunnil/Udham Ahirwar Madhi Tumen | Approved | 0 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005041/IF/22012035505852 — Kapildhara Koop Nirman Hariram/Dayachand Prajapati | Ongoing | 267533.14 | 0 | 2025-06-05
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005041/IF/22012035505869 — Kaplidhara Koop Nirman Harnarayan / Gopal Kurmi Nageshri | Approved | 0 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005041/IF/22012035505886 — Kapildhara Koop Nirman Lallu / Naval Ahirwar Nageshri | Approved | 0 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005041/IF/22012035505901 — Kapildhara Koop Nirman Lakhan/Dheeraj Singh Nageshri | Ongoing | 267533.14 | 0 | 2025-06-05
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005041/IF/22012035505914 — Kapildhara Koop Nirman Rahul/Balveer Yadav Nageshri | Approved | 0 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005041/IF/22012035505938 — Kapildhara Koop Nirman Bhag Bai/Bhola Ahirwar Madhi Tumen | Approved | 0 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1748005041/IF/22012035505983 — Kapildhara Koop Nirman Raju urf Rajkumar /Sukhram Kurmi Nageshri | Approved | 0 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748005041/IF/IAY/122390 — Construction of IAY House -IAY REG. NO. MP-48-005-041-002/2 | Approved | 27000 | 0 | 2016-01-27
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005041/IF/IAY/5159624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117648640 | Physically Completed | 27000 | 20400 | 2025-04-01 | 2026-10-01
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005041/IF/IAY/5181313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117162041 | Physically Completed | 27000 | 0 | 2025-04-01 | 2026-09-27
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005041/IF/IAY/6005141 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144327658 | Physically Completed | 23490 | 13200 | 2026-04-23 | 2026-08-02
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005041/IF/IAY/6005581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117649177 | Physically Completed | 27000 | 12300 | 2026-04-15 | 2026-09-20
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005041/IF/IAY/6005595 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123525987 | Ongoing | 27000 | 0 | 2026-04-23
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005041/IF/IAY/6005852 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105588095 | Physically Completed | 27000 | 20100 | 2026-04-02 | 2026-09-13
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005041/IF/IAY/6006358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124484392 | Physically Completed | 27000 | 14700 | 2026-04-02 | 2026-09-27
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005041/IF/IAY/6006456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113999051 | Physically Completed | 27000 | 18000 | 2026-04-02 | 2026-08-30
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005041/IF/IAY/6006458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113999101 | Ongoing | 27000 | 14400 | 2026-05-05
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005041/IF/IAY/6007023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104942960 | Physically Completed | 27000 | 13200 | 2026-04-02 | 2026-10-01
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005041/IF/IAY/6007803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105586824 | Ongoing | 27000 | 0 | 2026-04-15
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005041/IF/IAY/6007975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149215900 | Physically Completed | 27000 | 0 | 2026-04-23 | 2026-10-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005041/IF/IAY/6008131 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126760442 | Ongoing | 27000 | 12300 | 2026-05-05
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005041/IF/IAY/6008202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113998840 | Physically Completed | 27000 | 14700 | 2026-04-02 | 2026-10-01
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005041/IF/IAY/6008295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117649205 | Physically Completed | 27000 | 16200 | 2026-04-15 | 2026-09-20
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005041/IF/IAY/6011002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106124130 | Ongoing | 27000 | 12600 | 2026-04-02
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005041/IF/IAY/6011003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106124149 | Physically Completed | 27000 | 18000 | 2026-04-23 | 2026-10-01
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1748005041/WC/22012035224813 — कूप निर्माण मुक्तिधाम के पास मढ़ी तूमेन | Approved | 0 | 0 | 2024-08-19
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1748005041/WC/22012035246191 — Parcolation Tank Nale Ke Pass Nageshri | Approved | 0 | 0 | 2025-01-24
ASHOK NAGAR / ASHOKNAGAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1748/RC/22012034611234 — Maintenance of CMGSY Road Ashoknagar Vidisa road se Bamuriya Dangi | Ongoing | 393000 | 0 | 2022-11-07