## Work List
Exported on: 2026-09-15 11:03:23
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: AMKHEDA SUKHA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005049/IF/22012035414771 — Khet talab nirman karya parvat singh ke khet ke pas | Ongoing | 248683.23 | 0 | 2025-05-02
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1748005049/IF/22012035568711 — Koop nirman karya gulab bai hamidpur | Ongoing | 322434.5 | 0 | 2025-07-02
ASHOK NAGAR / ASHOKNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/1378249 — Construction of IAY House -IAY REG. NO. MP1296911 | Ongoing | 27000 | 0 | 2018-09-10
ASHOK NAGAR / ASHOKNAGAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/1511905 — Construction of IAY House -IAY REG. NO. MP1428533 | Ongoing | 27000 | 0 | 2020-04-01
ASHOK NAGAR / ASHOKNAGAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/2427309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5025537 | Approved | 27000 | 0 | 2020-05-01
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/4544342 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106629016 | Ongoing | 27000 | 0 | 2025-02-12
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/4545609 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106630160 | Ongoing | 27000 | 0 | 2024-12-20
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/4836235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151116169 | Ongoing | 27000 | 0 | 2024-12-20
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/5096883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145209009 | Ongoing | 27000 | 0 | 2025-04-08
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/5526379 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145209348 | Ongoing | 27000 | 0 | 2025-05-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6124930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126642252 | Ongoing | 27000 | 1800 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6138667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123455222 | Ongoing | 27000 | 7800 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6139675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106626948 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6139677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106627451 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6150747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151126942 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6152638 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151116404 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6152640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151119161 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6152641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151120754 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6152642 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151121073 | Ongoing | 27000 | 7800 | 2026-07-06
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6152645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151128117 | Ongoing | 27000 | 7800 | 2026-07-21
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6158498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151115130 | Ongoing | 27000 | 11400 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6164375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114064110 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6167766 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145209216 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6169481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123464752 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6169830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126639558 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6171226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151117395 | Ongoing | 27000 | 3900 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6174481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151119973 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6183510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151114237 | Ongoing | 27000 | 3900 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6184459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151127375 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6188540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145208424 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005049/IF/IAY/6189617 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106628264 | Ongoing | 27000 | 7500 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1748005049/WC/22012035305741 — Dugwell recharge nirman karya sarwzanik koop ke pas aamkheda | Approved | 0 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1748005049/WC/22012035305753 — Dugwell recharge nirman karya sarwzanik koop ke pas hamidpur | New | 0 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1748005049/WC/22012035305754 — Dugwell recharge nirman karya sarwzanik koop ke pas hamidpur | Approved | 0 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1748005067/RC/22012034826671 — sudoor sadak nirmad Goushala se main road ki or | Ongoing | 913000 | 0 | 2026-01-21