## Work List
Exported on: 2026-10-22 04:54:05
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BAGULYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ASHOK NAGAR / ASHOKNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1748005074/AV/22012034507345 — aganwadi bhyavan bagulya | Ongoing | 180000 | 0 | 2020-02-07
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1748005074/AV/22012034666799 — shanti dham gram panchayat Bagulya | Ongoing | 347299.82 | 0 | 2025-11-20
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1748005074/AV/22012034666800 — shanti dham Bagulya chakk | New | 0 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005074/IF/22012035401428 — khet talab Rambabu /parmal singh raghuwanshi | New | 0 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748005074/IF/22012035401466 — khet talab rajendra singh /kamarji | Approved | 0 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1748005074/IF/22012035567097 — constraction of PMAYG house mp106286005 | Ongoing | 23490 | 0 | 2026-05-22
ASHOK NAGAR / ASHOKNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/1030382 — Construction of IAY House -IAY REG. NO. MP2365290 | Approved | 27000 | 0 | 2017-04-26
ASHOK NAGAR / ASHOKNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/1032521 — Construction of IAY House -IAY REG. NO. MP2460511 | Approved | 27000 | 0 | 2017-04-26
ASHOK NAGAR / ASHOKNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/131792 — Construction of IAY House -IAY REG. NO. MP-48-005-074-001/16 | Approved | 27000 | 0 | 2016-02-09
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/4582335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118828135 | Ongoing | 27000 | 0 | 2025-02-14
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/4645485 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142599585 | Ongoing | 27000 | 0 | 2025-02-13
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/4989157 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105426521 | Physically Completed | 23490 | 0 | 2025-03-22 | 2026-07-26
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/5018123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126235108 | Physically Completed | 23490 | 0 | 2025-03-29 | 2026-07-26
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/5998784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125587971 | Ongoing | 27000 | 0 | 2026-04-06
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/5998832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143616122 | Ongoing | 27000 | 0 | 2026-05-22
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/5998833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143616298 | Ongoing | 27000 | 12600 | 2026-04-11
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/5998873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106299469 | Physically Completed | 27000 | 16200 | 2026-04-06 | 2026-10-01
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/5998956 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125587313 | Physically Completed | 27000 | 16500 | 2026-04-11 | 2026-10-01
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/5999171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126092303 | Ongoing | 27000 | 0 | 2026-04-11
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/5999243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125075203 | Ongoing | 27000 | 0 | 2026-05-01
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/5999264 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142599239 | Ongoing | 27000 | 18600 | 2026-04-06
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/5999265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142599345 | Physically Completed | 27000 | 10500 | 2026-04-11 | 2026-09-06
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/5999266 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142599499 | Ongoing | 27000 | 16800 | 2026-04-11
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/5999267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142599673 | Ongoing | 27000 | 16800 | 2026-04-11
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/5999269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142601406 | Ongoing | 27000 | 16800 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/5999270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142601969 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/5999793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118824598 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/5999897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142598182 | Physically Completed | 23490 | 11100 | 2026-04-06 | 2026-08-23
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6000228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147798326 | Ongoing | 27000 | 0 | 2026-04-06
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6000613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146928429 | Ongoing | 27000 | 0 | 2026-04-11
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6000614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146942279 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6000727 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106303985 | Ongoing | 27000 | 0 | 2026-04-11
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6000851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147756722 | Ongoing | 27000 | 16800 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6000893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147278786 | Ongoing | 27000 | 0 | 2026-04-11
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6000982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106292059 | Physically Completed | 27000 | 0 | 2026-05-01 | 2026-10-18
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6001036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106331558 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6001043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148359618 | Ongoing | 27000 | 0 | 2026-04-11
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6001791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147847937 | Ongoing | 27000 | 0 | 2026-04-06
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6001962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126242715 | Ongoing | 27000 | 18600 | 2026-04-11
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6002527 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118848614 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6002575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147895954 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6002906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126244141 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6002953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142600328 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6002954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142600443 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6002955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142600518 | Ongoing | 27000 | 16800 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6002956 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142600581 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6002989 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147298157 | Ongoing | 27000 | 16800 | 2026-05-01
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6003021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125780348 | Ongoing | 27000 | 0 | 2026-05-01
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6003208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142598283 | Ongoing | 27000 | 0 | 2026-04-11
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6003238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126075954 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6003302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142594007 | Ongoing | 27000 | 0 | 2026-05-01
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6003303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142597202 | Ongoing | 27000 | 0 | 2026-05-01
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6003304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142597492 | Ongoing | 27000 | 16800 | 2026-04-06
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6003305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142594723 | Ongoing | 27000 | 16800 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6003556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118804469 | Ongoing | 27000 | 16800 | 2026-04-06
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6003672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125779730 | Ongoing | 27000 | 0 | 2026-04-11
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6003736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146932574 | Ongoing | 27000 | 18900 | 2026-04-11
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6004244 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126235904 | Ongoing | 27000 | 16800 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6247601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106315853 | Approved | 27000 | 0 | 2026-04-06
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6264212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125838365 | Approved | 27000 | 0 | 2026-04-06
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6275429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146950139 | Approved | 27000 | 0 | 2026-02-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6275576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147234856 | Approved | 27000 | 0 | 2026-04-06
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6275578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147235004 | Approved | 27000 | 0 | 2026-02-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6276229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147248085 | Approved | 27000 | 0 | 2026-02-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6276871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147282398 | Approved | 27000 | 0 | 2026-02-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6287627 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148925508 | Approved | 27000 | 0 | 2026-02-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6297933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126092807 | Approved | 27000 | 0 | 2026-02-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6303887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142600668 | Approved | 27000 | 0 | 2026-02-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6307202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142595986 | Approved | 27000 | 0 | 2026-04-06
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6308650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125838143 | Approved | 27000 | 0 | 2026-04-06
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6308658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142599110 | Approved | 27000 | 0 | 2026-02-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6313054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147272798 | Approved | 27000 | 0 | 2026-02-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6313125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147234936 | Approved | 27000 | 0 | 2026-04-06
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6314823 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105887270 | Ongoing | 27000 | 0 | 2026-10-12
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6316536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142600763 | Approved | 27000 | 0 | 2026-04-06
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6317810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106332747 | Approved | 27000 | 0 | 2026-02-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6322185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148345801 | Approved | 27000 | 0 | 2026-02-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6328875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147296338 | Approved | 27000 | 0 | 2026-02-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6355940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142599756 | Approved | 27000 | 0 | 2026-02-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6397612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118857993 | Approved | 27000 | 0 | 2026-02-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6397724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147793620 | Approved | 27000 | 0 | 2026-02-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748005074/IF/IAY/6397776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147272861 | Approved | 27000 | 0 | 2026-02-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1748005074/LD/22012034944885 — shanti dham madhopur chak | New | 0 | 0 | 2024-10-22