## Work List
Exported on: 2026-08-29 17:23:57
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: PADAM GHATA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1748005093/IC/22012034890198 — Samudayak Koop Nirman Deprai Me | New | 0 | 0 | 2025-04-01
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005093/IF/22012035233469 — Khet Talav Nirman Kamal Singh Jatav Ke Khet Me | Approved | 348318.54 | 0 | 2024-06-13
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005093/IF/22012035233471 — Khet Talav Nirman Govandi Jatav Ke Khet Me | Approved | 348318.54 | 0 | 2024-06-13
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005093/IF/22012035318067 — Khet Talav Nirman Ravindra pal Ke khe me | Approved | 316160.38 | 0 | 2025-04-01
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005093/IF/22012035318068 — Khet Talav Nirman RamabuYadav Ke khet Me | Approved | 316160.38 | 0 | 2025-04-01
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005093/IF/22012035318079 — Khet Talav Nirma SangramSingh Yadav Ke Khet Me | Approved | 316160.38 | 0 | 2025-04-01
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1748005093/IF/22012035318080 — Hiteshi Koop Nirman Chukhra Ahirwar Ke Khet Me Kaithai | Approved | 322434.5 | 0 | 2025-04-01
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1748005093/IF/22012035321009 — Hiteshi Koop Nirman Karai Bai Yadav Ke Khet Me Kaithai | Approved | 0 | 0 | 2025-04-01
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1748005093/IF/22012035345819 — Hiteshi Koop Nirman Jagdeesh Bairagi Ke Khet Me Padamghata | Approved | 0 | 0 | 2025-04-01
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005093/IF/22012035661836 — Khet talab niraman karya Harveer yadav ke khet mein deprai | Approved | 180032.3 | 0 | 2026-01-26
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005093/IF/22012035661837 — Khet talab niraman kar Neetesh yadav ke khet mein | Approved | 199167.49 | 0 | 2026-01-26
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005093/IF/22012035661838 — Khet talab nirman karya digpal yadav ke khet mein kaithai | Approved | 199167.49 | 0 | 2026-01-26
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005093/IF/22012035661839 — Khet talab nirman karya Dayaram ahirwar ke khet mein | Approved | 199167.49 | 0 | 2025-10-02
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005093/IF/22012035661840 — Khet talab nirman karya anil Bairagi ke khet mein | Approved | 199167.49 | 0 | 2026-01-26
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005093/IF/22012035661842 — Khet talab Nirman karya Dayaram Ahirwar/chironja | Approved | 181052.1 | 0 | 2025-10-02
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005093/IF/22012035661843 — Khet talab nirman karya udhan ahirwar ke khet mein | Approved | 180363.22 | 0 | 2026-01-26
ASHOK NAGAR / ASHOKNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4038220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105656793 | Completed | 23490 | 0 | 2022-08-28 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4063890 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115091499 | Physically Completed | 23490 | 0 | 2022-08-28 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4292516 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123928313 | Physically Completed | 23490 | 0 | 2022-08-30 | 2026-07-26
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4305086 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123265490 | Ongoing | 27000 | 0 | 2024-10-31
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4541342 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105594002 | Ongoing | 27000 | 12000 | 2024-10-31
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4561011 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114997642 | Completed | 23490 | 1800 | 2024-10-31 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4597610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122559256 | Ongoing | 27000 | 0 | 2024-10-31
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4599018 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123073153 | Completed | 23490 | 0 | 2024-10-31 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4600013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122908262 | Ongoing | 27000 | 6000 | 2025-02-18
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4600081 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122925867 | Physically Completed | 23490 | 1800 | 2024-10-31 | 2026-08-15
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4600625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123483719 | Ongoing | 27000 | 0 | 2024-10-31
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4619456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126428258 | Physically Completed | 23490 | 0 | 2024-10-31 | 2026-07-26
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4637619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130512596 | Ongoing | 27000 | 0 | 2025-02-18
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4986428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103494031 | Completed | 23490 | 0 | 2025-03-20 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4986430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103495121 | Completed | 23490 | 8400 | 2025-03-20 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4988293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105548362 | Completed | 23490 | 0 | 2025-03-20 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4988296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105548592 | Physically Completed | 23490 | 3600 | 2025-03-20 | 2026-08-06
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4988400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105601136 | Ongoing | 27000 | 0 | 2025-03-26
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4988881 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102354092 | Physically Completed | 23490 | 0 | 2025-03-20 | 2026-08-06
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4989665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106578606 | Ongoing | 27000 | 0 | 2025-03-20
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/4999908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116985316 | Completed | 23490 | 1800 | 2025-03-20 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5001367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117895242 | Completed | 23490 | 5100 | 2025-03-20 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5001371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117895817 | Physically Completed | 23490 | 0 | 2025-03-26 | 2026-07-26
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5004216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118359742 | Completed | 23490 | 3600 | 2025-03-20 | 2026-08-20
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5006742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119481739 | Ongoing | 27000 | 4200 | 2025-03-20
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5006744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119481931 | Completed | 23490 | 2100 | 2025-03-20 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5006751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119483658 | Completed | 23490 | 5400 | 2025-03-20 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5006754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119484555 | Physically Completed | 23490 | 0 | 2025-03-20 | 2026-08-06
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5009013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120558762 | Completed | 23490 | 0 | 2025-03-26 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5009119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121835680 | Physically Completed | 23490 | 1200 | 2025-03-20 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5010963 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123074350 | Completed | 23490 | 6900 | 2025-03-20 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5011642 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122903204 | Completed | 23490 | 14700 | 2025-03-20 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5011683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122928479 | Ongoing | 27000 | 4200 | 2025-03-20
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5011694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122934919 | Ongoing | 27000 | 8400 | 2025-03-20
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5012046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123251085 | Ongoing | 27000 | 0 | 2025-03-20
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5012064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123258006 | Completed | 23490 | 1500 | 2025-03-26 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5012085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123271818 | Completed | 23490 | 1800 | 2025-03-26 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5012090 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123276225 | Physically Completed | 23490 | 1800 | 2025-03-20 | 2026-07-26
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5013027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123485895 | Completed | 23490 | 3600 | 2025-03-20 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5013478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122827527 | Physically Completed | 23490 | 3600 | 2025-03-26 | 2026-08-06
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5021266 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126428700 | Completed | 23490 | 2100 | 2025-03-20 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5082302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115102707 | Physically Completed | 23490 | 1800 | 2025-03-26 | 2026-08-06
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5683389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119482670 | Ongoing | 27000 | 4200 | 2025-07-24
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5683460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119090857 | Ongoing | 27000 | 0 | 2025-07-24
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5683462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122829032 | Completed | 23490 | 13200 | 2025-07-24 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5683490 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106201505 | Completed | 23490 | 3300 | 2025-07-24 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5683510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105946173 | Completed | 23490 | 1800 | 2025-07-24 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5683518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106791738 | Ongoing | 27000 | 0 | 2025-08-27
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5683701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119482981 | Physically Completed | 23490 | 0 | 2025-07-24 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5687730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122913490 | Physically Completed | 23490 | 3600 | 2025-08-27 | 2026-07-26
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/5687850 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122932284 | Completed | 23490 | 1800 | 2025-08-27 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6004346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116429815 | Ongoing | 27000 | 11400 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6004347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116430275 | Ongoing | 27000 | 3600 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6004348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116430360 | Ongoing | 27000 | 8400 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6004478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105594090 | Ongoing | 27000 | 4200 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6004480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105599654 | Ongoing | 27000 | 3900 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6004696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105866489 | Ongoing | 27000 | 0 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6005006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149915930 | Ongoing | 27000 | 1800 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6005045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106789409 | Physically Completed | 23490 | 8700 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6005046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106791477 | Ongoing | 27000 | 3600 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6005050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106793705 | Completed | 23490 | 5700 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6005347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113678505 | Ongoing | 27000 | 3600 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6005628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122559668 | Ongoing | 27000 | 0 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6005662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122934064 | Completed | 23490 | 3900 | 2026-04-04 | 2026-08-17
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6005737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116984577 | Completed | 23490 | 5700 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6005766 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119554785 | Ongoing | 27000 | 4200 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6005844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124579156 | Ongoing | 27000 | 3600 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6005897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121837892 | Ongoing | 27000 | 4200 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6005903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115091976 | Ongoing | 27000 | 8400 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6005935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124034121 | Ongoing | 27000 | 0 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6005952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117895878 | Physically Completed | 23490 | 2100 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122930904 | Physically Completed | 23490 | 2100 | 2026-04-04 | 2026-08-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122931814 | Ongoing | 27000 | 4200 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122932780 | Physically Completed | 23490 | 3900 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122933668 | Ongoing | 27000 | 3900 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122941801 | Ongoing | 27000 | 4200 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122828537 | Physically Completed | 23490 | 5100 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122829562 | Ongoing | 27000 | 3600 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122830078 | Physically Completed | 23490 | 12000 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119482659 | Ongoing | 27000 | 5700 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119482790 | Completed | 23490 | 16500 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119482800 | Ongoing | 27000 | 8400 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119482935 | Completed | 23490 | 16500 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119483127 | Ongoing | 27000 | 8400 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119483234 | Completed | 23490 | 16200 | 2026-04-04 | 2026-08-20
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119483340 | Ongoing | 27000 | 0 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006345 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119483429 | Physically Completed | 23490 | 0 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119483669 | Completed | 23490 | 8400 | 2026-04-04 | 2026-08-20
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119484589 | Ongoing | 27000 | 8400 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106355676 | Physically Completed | 23490 | 1200 | 2026-04-04 | 2026-08-23
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106375099 | Ongoing | 27000 | 3600 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6006944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103494523 | Physically Completed | 23490 | 0 | 2026-04-04 | 2026-08-23
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106787424 | Ongoing | 27000 | 1800 | 2026-04-05
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106787659 | Physically Completed | 23490 | 11400 | 2026-04-05 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007166 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119483798 | Completed | 23490 | 5700 | 2026-04-04 | 2026-08-20
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106787046 | Physically Completed | 23490 | 8100 | 2026-04-04 | 2026-08-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106787075 | Ongoing | 27000 | 1800 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106787291 | Ongoing | 27000 | 1800 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106788484 | Ongoing | 27000 | 1800 | 2026-04-05
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106360138 | Physically Completed | 23490 | 3600 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117894167 | Physically Completed | 23490 | 1800 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119087005 | Ongoing | 27000 | 4200 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007633 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119091280 | Ongoing | 27000 | 8400 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123245369 | Ongoing | 27000 | 3600 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123253138 | Ongoing | 27000 | 3600 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123253785 | Ongoing | 27000 | 0 | 2026-04-19
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123255477 | Ongoing | 27000 | 10200 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123278311 | Ongoing | 27000 | 3600 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130484640 | Ongoing | 27000 | 0 | 2026-04-19
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106376236 | Ongoing | 27000 | 3600 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106376244 | Ongoing | 27000 | 10200 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105589384 | Physically Completed | 23490 | 5700 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123248585 | Ongoing | 27000 | 10200 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6007916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123249420 | Completed | 23490 | 12000 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6008196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117894009 | Physically Completed | 23490 | 3600 | 2026-04-04 | 2026-08-06
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6008197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117894078 | Completed | 23490 | 3600 | 2026-04-04 | 2026-08-20
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6008669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105593801 | Physically Completed | 23490 | 3900 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6008670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105593950 | Physically Completed | 23490 | 3900 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6008671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105594045 | Ongoing | 27000 | 4200 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6008757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103493525 | Ongoing | 27000 | 4200 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6008886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123926653 | Physically Completed | 23490 | 1800 | 2026-04-19 | 2026-08-06
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116985445 | Completed | 23490 | 5700 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009092 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123243778 | Completed | 23490 | 9300 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126928948 | Physically Completed | 23490 | 3600 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106789740 | Completed | 23490 | 12000 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106791385 | Ongoing | 27000 | 1800 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106791418 | Ongoing | 27000 | 3600 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106788959 | Physically Completed | 23490 | 3600 | 2026-04-05 | 2026-08-06
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119481789 | Ongoing | 27000 | 4200 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119481916 | Completed | 23490 | 0 | 2026-04-04 | 2026-08-20
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119481991 | Ongoing | 27000 | 4200 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119482062 | Physically Completed | 23490 | 0 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119482078 | Ongoing | 27000 | 4200 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119482130 | Ongoing | 27000 | 0 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119482296 | Completed | 23490 | 8400 | 2026-04-04 | 2026-08-20
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119482307 | Completed | 23490 | 16500 | 2026-04-04 | 2026-08-20
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119482366 | Ongoing | 27000 | 4200 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122903719 | Ongoing | 27000 | 1800 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123234550 | Ongoing | 27000 | 0 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123246341 | Physically Completed | 23490 | 3600 | 2026-04-04 | 2026-08-23
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009571 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122905860 | Ongoing | 27000 | 0 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123231847 | Completed | 23490 | 5700 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115091856 | Ongoing | 27000 | 8400 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6009848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116429590 | Physically Completed | 23490 | 11400 | 2026-05-08 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6010253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116984298 | Ongoing | 27000 | 3900 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6010296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123276706 | Physically Completed | 23490 | 12000 | 2026-04-04 | 2026-08-02
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6010344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123266464 | Physically Completed | 23490 | 7800 | 2026-04-04 | 2026-08-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6010513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116429923 | Ongoing | 27000 | 3900 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6010567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105656752 | Ongoing | 27000 | 4200 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6010612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105946532 | Completed | 23490 | 10200 | 2026-04-19 | 2026-08-20
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6010658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122942161 | Physically Completed | 23490 | 3900 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6010780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107072027 | Ongoing | 27000 | 9600 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6010890 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122909054 | Ongoing | 27000 | 1800 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6011004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106355797 | Completed | 23490 | 4800 | 2026-04-19 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6011005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106355812 | Completed | 23490 | 8700 | 2026-04-19 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6011006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106355830 | Ongoing | 27000 | 3600 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6011007 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105914729 | Physically Completed | 23490 | 7800 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6011008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118360415 | Ongoing | 27000 | 3600 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6011009 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106785724 | Ongoing | 27000 | 1800 | 2026-04-05
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6011010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105596499 | Ongoing | 27000 | 0 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6011011 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105596646 | Ongoing | 27000 | 4200 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6011012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105596795 | Ongoing | 27000 | 8400 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6011013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105866331 | Ongoing | 27000 | 1800 | 2026-04-19
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6011018 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106374393 | Ongoing | 27000 | 1800 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6011062 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115101696 | Ongoing | 27000 | 3900 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6011063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105912387 | Physically Completed | 23490 | 7500 | 2026-04-04 | 2026-08-02
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6011064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103495858 | Physically Completed | 23490 | 3900 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6011066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113676195 | Completed | 23490 | 5700 | 2026-04-04 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005093/IF/IAY/6011165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106201085 | Ongoing | 27000 | 1800 | 2026-04-04
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1748005093/WC/22012035242324 — Percolation tank nirman karya gaushala charagaha ke pass | Approved | 318392.38 | 0 | 2024-10-02
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1748005093/WC/22012035242328 — Percolation tank nirman karya Maherwan Kevat ke khet ke pass | Approved | 318392.38 | 0 | 2024-10-02
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1748005093/WC/22012035242332 — Percolation tank nirman karya Partab Kevat ke khet ke pass | Approved | 318392.38 | 0 | 2024-10-02
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1748005093/WC/22012035242339 — Percolation tank nirman karya Kamal Singh Jatav ke khet ke pass | Approved | 318392.38 | 0 | 2024-10-02
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1748005093/WC/22012035242341 — Percolation tank nirman karya Govandi Jatav ke khet ke pass | Approved | 318392.38 | 0 | 2024-10-02
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1748005093/WC/22012035242345 — Percolation tank nirman Nadi ke pass | Approved | 318392.38 | 0 | 2024-10-02
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1748005093/WH/22012034943281 — Navin Talav Nirman Kary Kaithai Bale Nale par kaithai | Approved | 0 | 0 | 2025-01-25