## Work List
Exported on: 2026-10-01 21:34:35
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: JHEELA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1748005098/IC/22012034889243 — samudayik koop Nirman gram jheela | Ongoing | 588165.42 | 0 | 2025-03-25
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1748005098/IC/22012034892523 — sarvjanik koop nirman peena nale ke pas jheela | Ongoing | 605674.76 | 0 | 2026-03-07
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005098/IF/22012035421410 — Khet talab nirman Vishal/Toran | Approved | 316160.38 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005098/IF/22012035421724 — Khe talab nirman karya shimla bai / pahalwan | Approved | 316160.38 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005098/IF/22012035421769 — Khe talab nirman karya Maro bai / chatar singh | Approved | 0 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005098/IF/22012035421849 — Khet talab nirman karya prakash /toran | Approved | 0 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005098/IF/22012035423202 — khet talab ramveer/lachchhu | Approved | 0 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005098/IF/22012035423241 — khet talab Dinesh/jashman | Approved | 0 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1748005098/IF/22012035423319 — khet talab Ramsevak/Halkaiya | Approved | 0 | 0 | 2025-04-14
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1748005098/IF/22012035583955 — Ek Bagiya Maa Ke naam Sunita Bai/Ramesh gram Jheela | Ongoing | 280503.33 | 12600 | 2025-09-10
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1748005098/IF/22012035591831 — Ek Bagiya Maa Ke naam Vandana/Hariom Ahirwar | Ongoing | 271689.33 | 8400 | 2025-09-10
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1748005098/IF/22012035593353 — Ek bagiya Maa ke naam VIMLA BAI/GOPAL SINGH Ahirwar | Ongoing | 271614.75 | 11100 | 2025-09-10
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1748005098/IF/22012035595852 — Ek Bagiya Maa Ke naam Sunita Sahu/Ramsingh | Ongoing | 266577.25 | 50020 | 2025-11-24
ASHOK NAGAR / ASHOKNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/119489 — Construction of IAY House -IAY REG. NO. MP-48-005-098-001/83 | Approved | 27000 | 0 | 2016-01-22
ASHOK NAGAR / ASHOKNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/196715 — Construction of IAY House -IAY REG. NO. MP-48-005-098-001/103 | Approved | 27000 | 0 | 2016-03-02
ASHOK NAGAR / ASHOKNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/3662493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117003003 | Approved | 27000 | 0 | 2022-04-23
ASHOK NAGAR / ASHOKNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/3700433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141267 | Ongoing | 27000 | 0 | 2022-09-12
ASHOK NAGAR / ASHOKNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/3882667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143090886 | Ongoing | 27000 | 0 | 2022-09-12
ASHOK NAGAR / ASHOKNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/4036729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105947881 | Ongoing | 27000 | 0 | 2022-08-31
ASHOK NAGAR / ASHOKNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/4039055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103639751 | Ongoing | 27000 | 0 | 2022-08-29
ASHOK NAGAR / ASHOKNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/4337890 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105745070 | Physically Completed | 27000 | 9600 | 2022-08-31 | 2026-09-27
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/4408072 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143090908 | Ongoing | 27000 | 0 | 2026-05-08
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/4545864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106140868 | Ongoing | 27000 | 0 | 2024-09-30
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/4545875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141264 | Ongoing | 27000 | 18900 | 2024-09-30
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/4545877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141488 | Ongoing | 27000 | 0 | 2024-09-30
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/4869764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141751 | Ongoing | 27000 | 18300 | 2025-02-18
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/4990054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106140764 | Ongoing | 27000 | 0 | 2025-03-26
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/4990056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106140791 | Ongoing | 27000 | 14100 | 2025-03-26
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/4990058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141187 | Ongoing | 27000 | 14100 | 2025-03-26
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5085414 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127387961 | Ongoing | 27000 | 0 | 2025-03-26
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5085422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127393378 | Ongoing | 27000 | 14100 | 2025-03-26
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5296509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116036951 | Ongoing | 27000 | 1200 | 2025-08-12
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5478187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141507 | Ongoing | 27000 | 0 | 2025-08-12
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5521987 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106367103 | Ongoing | 27000 | 1200 | 2025-08-12
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5523451 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141037 | Ongoing | 27000 | 3600 | 2025-08-12
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5525775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127388400 | Ongoing | 27000 | 0 | 2025-08-12
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5626759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117002581 | Ongoing | 27000 | 8700 | 2025-08-12
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5627061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106140178 | Physically Completed | 23490 | 0 | 2025-08-12 | 2026-07-26
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5627066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105949451 | Ongoing | 27000 | 0 | 2025-08-12
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5627151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141623 | Physically Completed | 27000 | 0 | 2025-08-12 | 2026-09-07
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5627158 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122380513 | Physically Completed | 27000 | 9000 | 2025-08-12 | 2026-09-20
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5658068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141567 | Physically Completed | 23490 | 0 | 2025-08-12 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5674848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141785 | Ongoing | 27000 | 0 | 2025-08-12
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5689499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143088876 | Physically Completed | 23490 | 0 | 2025-08-12 | 2026-08-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5690209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141238 | Physically Completed | 23490 | 0 | 2025-08-12 | 2026-07-26
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5690376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141538 | Ongoing | 27000 | 4800 | 2025-08-12
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5998581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122380675 | Ongoing | 27000 | 12300 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5998594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106367263 | Ongoing | 27000 | 14100 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5998712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141500 | Ongoing | 27000 | 14100 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5998714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141814 | Ongoing | 27000 | 4800 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5999383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122383615 | Ongoing | 27000 | 16200 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5999384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122384069 | Ongoing | 27000 | 14100 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5999571 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105949427 | Ongoing | 27000 | 0 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5999840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117002178 | Ongoing | 27000 | 9300 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5999841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117002920 | Ongoing | 27000 | 13500 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5999842 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117002978 | Ongoing | 27000 | 20400 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5999843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117003047 | Ongoing | 27000 | 0 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/5999844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117003162 | Ongoing | 27000 | 18900 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/6000334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143089417 | Ongoing | 27000 | 18300 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/6000335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143090458 | Ongoing | 27000 | 0 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/6000336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143090578 | Ongoing | 27000 | 17700 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/6001997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122382604 | Ongoing | 27000 | 23100 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/6001998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122382776 | Ongoing | 27000 | 0 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/6002020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103757265 | Ongoing | 27000 | 0 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/6002025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141245 | Ongoing | 27000 | 16200 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/6002027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141573 | Ongoing | 27000 | 21000 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/6002028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141587 | Ongoing | 27000 | 0 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/6002030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106141663 | Ongoing | 27000 | 18900 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/6002486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105948033 | Physically Completed | 23490 | 0 | 2026-05-09 | 2026-07-26
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/6003127 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127392629 | Ongoing | 27000 | 0 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/6003306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105948492 | Ongoing | 27000 | 18300 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/6003453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127391124 | Ongoing | 27000 | 0 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/6003828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143088631 | Ongoing | 27000 | 18900 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/6004210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117002517 | Ongoing | 27000 | 0 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/6004211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117002649 | Ongoing | 27000 | 0 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1748005098/IF/IAY/6004212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117002730 | Ongoing | 27000 | 0 | 2026-05-09
ASHOK NAGAR / ASHOKNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1748005098/LD/22012034520464 — चारगृह ग्राम झीला | Ongoing | 1493590.37 | 0 | 2020-07-16
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1748005098/WC/22012035209080 — Pokhar nirman Prakash ke khet ke pas | Approved | 318392.38 | 0 | 2024-06-10
ASHOK NAGAR / ASHOKNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1748005098/WC/22012035223367 — Pokhar nirman Kamalsingh ke khet ke pas | Approved | 0 | 0 | 2024-08-16
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1748005098/WC/22012035328416 — contur trench jasoda bai ke khet ke pas siddh pahad par | Approved | 0 | 0 | 2026-01-26
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1748005098/WC/22012035328417 — contur trench kashiram ke khet ke pas ber bale pahad par | Approved | 0 | 0 | 2026-01-26
ASHOK NAGAR / ASHOKNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1748005098/WH/22012034945333 — तालाब जीर्णोद्धार कार्य ककराई रोड के पास ग्राम झीला | Ongoing | 958826.87 | 0 | 2026-03-06