## Work List
Exported on: 2026-10-23 20:17:06
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BILAKHEDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ASHOK NAGAR / MUNGAOLI | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1748007038/AV/22012034666805 — Shanti dham nirman kary Gram Bilakhedi | New | 0 | 0 | 2025-07-10
ASHOK NAGAR / MUNGAOLI | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1748007038/AV/22012034666806 — Shanti dham nirman kary Gram Rampur muhal | New | 0 | 0 | 2025-07-10
ASHOK NAGAR / MUNGAOLI | 2026-2027 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1748007038/AV/VB/22012034669490 — Shantidham nirman kary gram rampumuhal | New | 0 | 0 | 2026-04-14
ASHOK NAGAR / MUNGAOLI | 2026-2027 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1748007038/AV/VB/22012034669491 — Shantidham nirman kary gram Chamrai | New | 0 | 0 | 2026-04-15
ASHOK NAGAR / MUNGAOLI | 2026-2027 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1748007038/AV/VB/22012034669492 — Shantidham nirman kary gram Beelakhedi | New | 0 | 0 | 2026-04-14
ASHOK NAGAR / MUNGAOLI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in fields for Community | Plantation | 1748007038/DP/22012034611730 — community nutririon garden gram Bilakhedi | Ongoing | 1496932.19 | 0 | 2024-08-24
ASHOK NAGAR / MUNGAOLI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007038/IF/22012034658346 — Khet talab nirman brakbhan singh/bundel singh | Ongoing | 332962.02 | 0 | 2021-02-25
ASHOK NAGAR / MUNGAOLI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007038/IF/22012034658350 — khet talab nirman vikram singh/bundel singh | Ongoing | 332962.02 | 0 | 2021-02-25
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007038/IF/22012035463423 — Khettalab nirman kary Dalveer singh/Uttam singh | Approved | 0 | 0 | 2025-04-14
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007038/IF/22012035463432 — Khettalab nirman kary Malkhan singh/Mitthu singh | Approved | 0 | 0 | 2025-04-14
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007038/IF/22012035463445 — Khettalab nirman kary sultan singh/ gajraj singh | Approved | 0 | 0 | 2025-04-14
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007038/IF/22012035463454 — Khettalab nirman kary bhanu/ makhan singh | Ongoing | 351377.54 | 0 | 2025-06-22
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007038/IF/22012035463470 — Khettalab nirman kary khilan/ ishwar singh | Ongoing | 351377.54 | 0 | 2025-06-22
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007038/IF/22012035463480 — Khettalab nirman kary maniram/ kalyan singh | Approved | 351377.54 | 0 | 2025-04-14
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1748007038/IF/22012035649482 — Ek Bagiya Maa ke Naam Karai Bai | Approved | 0 | 0 | 2025-12-01
ASHOK NAGAR / MUNGAOLI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007038/IF/IAY/2161581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5558030 | Ongoing | 27000 | 0 | 2019-10-13
ASHOK NAGAR / MUNGAOLI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007038/IF/IAY/3252497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1346963 | Approved | 27000 | 0 | 2021-01-30
ASHOK NAGAR / MUNGAOLI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007038/IF/IAY/4063557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115897666 | Physically Completed | 23490 | 0 | 2024-03-12 | 2026-08-09
ASHOK NAGAR / MUNGAOLI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007038/IF/IAY/4078422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122388617 | Ongoing | 27000 | 0 | 2022-09-11
ASHOK NAGAR / MUNGAOLI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007038/IF/IAY/4085548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125575212 | Ongoing | 27000 | 0 | 2023-12-25
ASHOK NAGAR / MUNGAOLI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007038/IF/IAY/4088019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123194852 | Ongoing | 27000 | 0 | 2022-09-10
ASHOK NAGAR / MUNGAOLI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007038/IF/IAY/4148085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125581795 | Ongoing | 27000 | 0 | 2024-03-12
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007038/IF/IAY/5804174 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151992432 | Ongoing | 27000 | 0 | 2025-11-16
ASHOK NAGAR / MUNGAOLI | 2015-2016 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1748007038/SK/9993626454 — Bharat Nirman Rajeev Gandhi Sewa Kendra,BILAKHEDI | Ongoing | 1285000 | 0 | 2015-06-08
ASHOK NAGAR / MUNGAOLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1748007038/WC/22012035167805 — Stap dam nirman kary rajendra singh yadav ke khet ke pas sarve no. 282/2 gram charmrai | Ongoing | 459000 | 0 | 2025-06-11
ASHOK NAGAR / MUNGAOLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1748007038/WC/22012035194807 — Checkdam nirman kary jagdish ke khet ke pas bilakhedi | Ongoing | 1497270.45 | 0 | 2025-07-03
ASHOK NAGAR / MUNGAOLI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1748007038/WC/22012035214218 — Bolder check dam nirman kary jema nayak ke khet ke pas dangaliya | Approved | 206009.94 | 0 | 2024-04-24
ASHOK NAGAR / MUNGAOLI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1748007038/WC/22012035214223 — Bolder check dam nirman kary bhaiyalal/ ghuman ke khet ke pas | Approved | 206009.94 | 0 | 2024-04-24
ASHOK NAGAR / MUNGAOLI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1748007038/WC/22012035214225 — Bolder check dam nirman kary rama ke khet ke pas | Approved | 206009.94 | 0 | 2024-04-24
ASHOK NAGAR / MUNGAOLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1748007038/WC/22012035294544 — Dugwell recharge pit Jaypal/Sultan Gram bilakhedi | Approved | 25899.46 | 0 | 2025-04-14
ASHOK NAGAR / MUNGAOLI | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1748007044/AV/22012034666804 — Shantidham me teenshed evm chabutra nirman kary gram dangaliya | New | 0 | 0 | 2025-07-10