## Work List
Exported on: 2026-10-12 20:20:07
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: PARKANA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ASHOK NAGAR / MUNGAOLI | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1748007054/AV/22012034666904 — Shantidham nirman kary gram parkana | New | 0 | 0 | 2025-04-14
ASHOK NAGAR / MUNGAOLI | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1748007054/AV/22012034666906 — Shantidham nirman kary gram panchampur | New | 0 | 0 | 2025-04-15
ASHOK NAGAR / MUNGAOLI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1748007054/DP/22012034233590 — GP Parkana nandan phalodhwan Mangal singh/Murli singh | Ongoing | 150000 | 0 | 2016-09-01
ASHOK NAGAR / MUNGAOLI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1748007054/IF/22012034358233 — gp parkana plantation sadak kinare mukhy sadak se puliya ki or | Ongoing | 335000 | 0 | 2017-07-18
ASHOK NAGAR / MUNGAOLI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007054/IF/22012034555961 — khet talav nirman ratan / amol singh adibasi | Ongoing | 108814.67 | 0 | 2020-06-04
ASHOK NAGAR / MUNGAOLI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007054/IF/22012034992234 — Khet talab nirman kary ratan bai/ vikram singh | Ongoing | 322121.87 | 0 | 2024-02-29
ASHOK NAGAR / MUNGAOLI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007054/IF/22012035110542 — Khettalab nirman kary pratipal/ komaliya | Ongoing | 346836.59 | 0 | 2024-02-29
ASHOK NAGAR / MUNGAOLI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007054/IF/22012035110545 — Khettalab nirman kary munjo bai/ mokam | Ongoing | 346836.59 | 0 | 2024-02-29
ASHOK NAGAR / MUNGAOLI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007054/IF/22012035110547 — Khettalab nirman kary matarua/ anrat | Ongoing | 346836.59 | 0 | 2024-02-29
ASHOK NAGAR / MUNGAOLI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007054/IF/22012035110550 — Khettalab nirman kary rajbhan singh/ govind singh | Ongoing | 346836.59 | 0 | 2024-02-29
ASHOK NAGAR / MUNGAOLI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1748007054/IF/22012035111675 — Khettalab nirman kary kadori/ daloopa | Ongoing | 346836.59 | 0 | 2024-02-29
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1748007054/IF/22012035621649 — pmayg nirman kary malkhan kevat MP105084735 | Physically Completed | 23490 | 0 | 2025-09-26 | 2026-07-09
ASHOK NAGAR / MUNGAOLI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/1052282 — Construction of IAY House -IAY REG. NO. MP1025506 | Approved | 27000 | 0 | 2017-05-10
ASHOK NAGAR / MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/3820273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117381419 | Ongoing | 27000 | 0 | 2025-02-22
ASHOK NAGAR / MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4482212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152031774 | Ongoing | 27000 | 0 | 2025-02-10
ASHOK NAGAR / MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4482213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152031778 | Ongoing | 27000 | 0 | 2025-02-10
ASHOK NAGAR / MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4482214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152031781 | Ongoing | 27000 | 3600 | 2025-02-10
ASHOK NAGAR / MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4498568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152031785 | Ongoing | 27000 | 1800 | 2025-02-10
ASHOK NAGAR / MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4510076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152031773 | Ongoing | 27000 | 1800 | 2025-02-22
ASHOK NAGAR / MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4510084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152031789 | Completed | 27000 | 0 | 2025-03-01 | 2026-09-02
ASHOK NAGAR / MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4510093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152031808 | Ongoing | 27000 | 3600 | 2025-03-01
ASHOK NAGAR / MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4510103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152031821 | Ongoing | 27000 | 0 | 2025-03-01
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4542595 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105995040 | Ongoing | 27000 | 0 | 2025-04-28
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4544376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105074829 | Ongoing | 27000 | 0 | 2025-04-28
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4722541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146953760 | Ongoing | 27000 | 12600 | 2025-04-28
ASHOK NAGAR / MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4857940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152031815 | Ongoing | 27000 | 3600 | 2025-02-22
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4934602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105066192 | Ongoing | 27000 | 4500 | 2025-04-28
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4935037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102271616 | Ongoing | 27000 | 3600 | 2025-04-28
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4935038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102271682 | Ongoing | 27000 | 3600 | 2025-04-28
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4935492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103127285 | Ongoing | 27000 | 3000 | 2025-04-28
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4935530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103413149 | Ongoing | 27000 | 10800 | 2025-04-28
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4935541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103416614 | Ongoing | 27000 | 3600 | 2025-04-28
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4935764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103637513 | Ongoing | 27000 | 7200 | 2025-04-28
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4935838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103942106 | Ongoing | 27000 | 0 | 2025-05-02
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4935863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103962408 | Ongoing | 27000 | 0 | 2025-07-10
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4936128 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105069166 | Ongoing | 27000 | 3600 | 2025-04-09
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4939661 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105998192 | Ongoing | 27000 | 0 | 2025-05-02
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4940541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106225292 | Ongoing | 27000 | 0 | 2025-04-09
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4946082 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115899980 | Physically Completed | 23490 | 4500 | 2025-04-28 | 2026-08-02
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4949189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117378770 | Physically Completed | 23490 | 3000 | 2025-11-11 | 2026-07-26
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/4987106 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103127984 | Ongoing | 27000 | 14400 | 2025-04-28
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/5390850 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106408418 | Ongoing | 27000 | 0 | 2025-04-28
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/5667913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103941019 | Ongoing | 27000 | 14400 | 2025-08-27
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/5668294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105735897 | Ongoing | 27000 | 10800 | 2025-08-27
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/5668858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100959970 | Ongoing | 27000 | 3600 | 2025-08-27
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6176384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113703926 | Ongoing | 27000 | 18000 | 2026-05-09
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6178116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146955161 | Ongoing | 27000 | 18000 | 2026-05-09
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6179729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122462725 | Ongoing | 27000 | 18000 | 2026-05-02
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6180447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100964186 | Ongoing | 27000 | 12600 | 2026-05-02
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6181360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105067202 | Ongoing | 27000 | 7200 | 2026-05-19
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6183305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105996533 | Ongoing | 27000 | 18000 | 2026-05-09
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6183991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113496438 | Ongoing | 27000 | 0 | 2026-05-09
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6184719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129518700 | Ongoing | 27000 | 18000 | 2026-05-19
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6185115 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113706751 | Ongoing | 27000 | 18000 | 2026-05-02
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6185121 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105740555 | Ongoing | 27000 | 16200 | 2026-05-02
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6188267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146315463 | Ongoing | 27000 | 14400 | 2026-05-09
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6191529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103128508 | Ongoing | 27000 | 18000 | 2026-05-09
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6196041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113508313 | Ongoing | 27000 | 18000 | 2026-05-02
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6200084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146952190 | Ongoing | 27000 | 18000 | 2026-05-09
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6200640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122811555 | Ongoing | 27000 | 19800 | 2026-05-09
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6201565 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113729149 | Ongoing | 27000 | 18000 | 2026-05-09
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6209115 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146780312 | Ongoing | 27000 | 18000 | 2026-05-02
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6209215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113724807 | Ongoing | 27000 | 18000 | 2026-05-09
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6210892 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113700187 | Ongoing | 27000 | 0 | 2026-05-09
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6215260 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100964152 | Ongoing | 27000 | 9000 | 2026-05-02
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6215684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148101681 | Ongoing | 27000 | 21600 | 2026-05-02
ASHOK NAGAR / MUNGAOLI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/627366 — Construction of IAY House -IAY REG. NO. MP1137329 | Ongoing | 27000 | 0 | 2017-12-18
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6308703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113480912 | Approved | 27000 | 0 | 2026-03-22
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6309631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113474584 | Ongoing | 27000 | 0 | 2026-10-09
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6323321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114755778 | Approved | 27000 | 0 | 2026-03-21
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6341012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113832793 | Ongoing | 27000 | 25200 | 2026-08-13
ASHOK NAGAR / MUNGAOLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6341156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113714132 | Ongoing | 27000 | 25200 | 2026-08-13
ASHOK NAGAR / MUNGAOLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6397339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148101670 | Approved | 27000 | 0 | 2026-03-22
ASHOK NAGAR / MUNGAOLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/6405635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102254470 | Approved | 27000 | 0 | 2025-03-02
ASHOK NAGAR / MUNGAOLI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1748007054/IF/IAY/904801 — Construction of IAY House -IAY REG. NO. MP2203555 | Ongoing | 27000 | 0 | 2019-02-09
ASHOK NAGAR / MUNGAOLI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1748007054/RC/22012034559335 — Sudur Sadak Nirman Hariram lodhi ke makan se Mohiya nale tak gram parkana | Ongoing | 1436147.23 | 0 | 2021-06-20
ASHOK NAGAR / MUNGAOLI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1748007054/RC/22012034627288 — Cc road nirman kary middle school prangad me | Ongoing | 40717 | 0 | 2024-03-05
ASHOK NAGAR / MUNGAOLI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1748007054/RC/22012034656769 — Cc road nirman kary hanuman ji maharaj mandir prangad me | Ongoing | 38770 | 0 | 2024-03-05
ASHOK NAGAR / MUNGAOLI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1748007054/RC/22012034656770 — Cc road nirman kary hanuman ji mandir prangad me parkana chak | Ongoing | 31791 | 0 | 2024-03-05
ASHOK NAGAR / MUNGAOLI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1748007054/RS/22012034706298 — Nali nirman kary kailash ke makan se nadi ki or | Ongoing | 55046 | 0 | 2024-03-05
ASHOK NAGAR / MUNGAOLI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1748007054/WC/22012034625880 — LWM Sokhta gadda nirman prathmik vidhyalay ke pas | Ongoing | 14467.3 | 0 | 2021-06-06
ASHOK NAGAR / MUNGAOLI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1748007054/WC/22012035194771 — Check dem nirman Rampal Yadav ke khet ke pas | Ongoing | 1497270.45 | 0 | 2024-03-17
ASHOK NAGAR / MUNGAOLI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1748007054/WC/22012035308479 — Dugwell Recharge pit saskiye koop panha wale ke pas | Approved | 25899.46 | 0 | 2025-04-14